## Table 1
VO No. | SD No. | Variation description | Final Claimed Amount | Amount claimed in SOD (AED) | Not certified but agreed by Ishtar | Not confirmed as agreed by Ishtar but certified in IPC 65 | Appears Agreed / Not agreed | Disputed value | Initial Submission, Letter Ref. | Date received by SBJV | SBJV Response | Current status of the VO (i.e who stopped responding) | Mr Fitch's understanding of the claimed amount (AED) | Fitch Assessment Values (AED) | Clarke's Qty comments | Rate comments
1 | SOD 4 | VO No. 01 Additional Layer of Gypsum Board in to the Wall type 1.12 and 1.12.2 in Residence Tower | 2099283.12 | 2099283.12 |  |  | Not agreed | 2099283.12 | ID/C4242/UW/5073R1/18 | 8 Feb 2018. No received stamp on the Rev 1 submission. | SBJV responded and provided Ishtar with the Engineer's determination and Cost consultant's assessments. Ishtar responded stating that the Employer has not considered certain documents. SBJV responded noting the documents referred to did not relate to the claim. | Have not seen a response from Ishtar after SBJV noted the additional documents referred to did not relate to the claim. | 2099283.12 | 762381.91 | Mr. Fitch applied his assessment based on SBJV Letter Ref. RAP-SBJ-DMC- 2.12.26-21-21149, where SBJV determined a valuation of the variation at AED 762,381.91.
2 | SOD 4 | VO No. 02 Hollow Block changed to Solid Block at Basement Area in Podium | 25232 | 25232 | 25232.3 |  | Agreed | -0.3 | ID/C4242/ST/5170/18 |  | Ishtar accepted the valuation of this VO in the amount of AED 25,232.3 (Excl. 5% for SBJV) in letter ID/C4242/MZ/6424/19. |  | 25232 | 12005.7 | Fitch taken as claimed by Ishtar w/o profit
3 | - | VO 3# - Additional Manpower for MEP incorporation in M/s Ishtar Drawing. | 166408 |  | Incl. in VO 13 |  | N/A | N/A | `ID-C4242-ST-5172-18 | 2018-04-04 | N/A, see VO 13 below. | Included in VO 13
4 | - | VO No. 04 Additional Reinforcement for RF Metal Door Fixing in (Basement Floor) | 143162 |  | 143161.9 |  | Agreed | 0.1 | ID/C4242/ST/5185/18 | 2018-03-13 | SBJV issued the Cost Consultant's assessment on 16 Nov 2020 (RAP/SBJ/DMC/2.12.26/20/19947) in the amount of AED 150,320.10 (143,161.90 + 5% for SBJV).
5 | - | VO 15# - Rectification of Damages caused on the installed partitions by other sub-contractors | 13609.86 |  | Incl. in VO 35 |  | N/A | N/A | ID-C4242-ST-5285-18 | 2018-07-15 | N/A, see VO 15 below. | Included in VO 35
6 | - | VO No. 06 CIP 101 (EIP 0278) Change partially Constructed DEWA Room from Hollow to Solid Block in Podium | 233210 |  | 162911.22 | 233209.52 | Agreed | 0.48 | ID/C4242/ST/5880/18 | 2018-11-28 | SBJV claimed AED 400,696.93 which Arcadis responded with AED 162,911.22 and Ishtar's response was AED 233,209.24. | Amount certified in IPC 65 is as claimed. Appears agreed.
7 | - | VO No. 07 Release of Updated Architectural IFC Drawings – Basement Kitchen in Podium | 94870 |  | 94870 |  | Agreed | - | ID/C4242/ST/5106/18 | 2018-06-17 | SBJV issued a variation (SVO-0041) in the amount of AED 94,870 (letter TRA/SBJ/FLH/2.12.26/19/08306) | Amount certified in IPC 65 is as claimed. Appears agreed.
8 | SOD 2 | VO No. 08 Hotel Tower - Change of Door Nib Size in Hotel Tower | 86944 | 86944 |  |  | Not agreed | 86944 | ID/C4242/ST/5467/18 |  |  |  | 86944 | 79040 | Fitch taken as claimed by Ishtar w/o profit
9 | - | VO No. 09 Release of Updated Architectural IFC Drawings - Empower Amendments in Podium | 87960 |  | 87960.11 |  | Agreed | -0.11 | ID/C4242/ST/5468/18 |  | Ishtar accepted Cost Consultant's amount of AED 87,960.11 on 14 Nov 2018 via letter ID/C4242/ST/5874/18
10 | - | VO 10# - Masonry Wall At Basement Zone 13&14 | 137239.55 |  |  |  | Not agreed | 137239.55 | ID-C4242-ST-5469-18 | No received stamp from SBJV. | Unable to determine if SBJV (i) received and (ii) responded, to letter ID/C4242/ST/5469/18. | TBC
11 | - | VO No. 11 Cl 039 Aesthetic Improvements & Consolidation of MEP Services in Carpark in Podium | 92275.76 |  | 92276 |  | Agreed | -0.24 | ID-C4242-ST-5561-18 | 2018-07-28 | Ishtar accepted the valuation of this VO in the amount of AED 92,276 (Excl. 5% for SBJV) in letter ID/C4242/ST/7719/2020.
12 | - | VO No. 12 Release of IFC Information to Proceed for Residences in Podium | 184430 |  | 184430.33 |  | Agreed | -0.33 | ID/C4242/MZ/5496/18 | 2018-07-11 | Ishtar accepted Cost Consultant's amount of AED 184,430.33 on 14 Nov 2018 via letter ID/C4242/ST/5874/18
13 | SOD 2 | Additional Drawings to Incorporate MEP Requirements in Engineering | 296887 | 296887 |  |  | Not agreed | 296887 | ID/C4242/ST/5497/18 |  |  |  | 296887 | 372527 | Fitch taken as claimed by Ishtar. | 0
14 | SOD 4 | VO No. 14 Additional Wall Noggin for TV. Bracket installation in Type A & B Guestrooms in Hotel Tower | 18130.2 | 15458.4 |  |  | Not agreed | 18130.2 | ID/C4242/ST/5284/18 |  |  |  | 18130.2 | 16482 | Fitch taken as claimed by Ishtar w/o profit | 0
15 | - | VO 15# - Rectification of Damages caused on the installed partitions by other sub-contractors | 13609.86 |  | Incl. in VO 35 |  | N/A | N/A | ID-C4242-ST-5285-18 | 2018-07-15 | N/A, see VO 35 below. | Included in VO 35
16 | SOD 4 | VO No. 16 Residential units - Discrepancy between A23 Series and Approved FLS Drawings (Shaft Walls) in Residence Tower | 68006.64 | 68006.64 |  |  | Not agreed | 68006.64 | ID/C4242/MZ/5520/18 |  |  |  | 68006.64 | 78492.57 | Fitch taken as claimed by Ishtar w/o profit | 0
17 | - | VO No. 17 F3 Uncoordinated Design- Sliding Door Partition Thickness in Residence Tower | 1006560.61 |  | 1006560.61 |  | Agreed | - | ID-C4242-ST-5560-18 |  | Ishtar accepted the valuation of this VO in the amount of AED 1,006,560.61 (Excl. 5% for SBJV) in letter ID/C4242/ST/7442/20.
18 | - | WHAT IS VO |  |  | N/A |  | N/A | N/A | ` | N/A | N/A | N/A
19 | - | VO No. 19 Residential Units - (Level 14-17)- Additional Wall Missing Information in Residence Tower | 3186.81 |  | 3261.46 |  | Agreed | -74.65 | ID/C4242/MZ/5548/18 | 2018-07-26 | SBJV issued the Cost Consultant's assessment on 2 Oct 2018 (RAP/SBJ/RSM/2.12.26/18/05440) in the amount of AED 3,424.53 (3,261.46 + 5% for SBJV).
20 | SOD 4 | VO No. 20 - Podium Levels - Discrepancy between IFC A10 Series and Approval FLS Drawing in Podium | 55318.67 | 55318.67 | 55318.67 |  | Agreed | - | ID/C4242/MZ/5549/18 | 2018-07-26 | Ishtar accepted Cost Consultant's amount of AED 55,318.67 on 14 Nov 2018 via letter ID/C4242/ST/5874/18 |  | 55318.67 | 65705.44 | Fitch taken as claimed by Ishtar w/o profit | 0
21 | - | VO No.21 - Change of 1.8 wall type to 7.1 in HT1,2 and 3 in level 5,6 and 8 Room type ( A6.2, A6.2R, A5.2, A5.2R, A7.2, A7.2R ) in Hotel Tower | 36909 |  | 36909 |  | Agreed | - | ID/C4242/MZ/5607/18 | 2018-08-09 | Ishtar accepted the valuation of this VO in the amount of AED 36,909 (Excl. 5% for SBJV) in letter ID/C4242/MZ/6418/19.
22 | - | VO No. 22 DEWA Mobile Generator Room IFC in Podium | 26222 |  | 26222 |  | Agreed | - | ID/C4242/MZ/5859/18 |  | SBJV issued a SVO (see TRA/SBJ/FLH/2.12.26/20/16689) in the amount of AED 26,222 after Ishtar accepted the Cost Consultant's assessment in letter ID/C4242/MZ/6003/19 (without 5% for SBJV). | Amount certified in IPC 65 is as claimed. Appears agreed.
23 | - | VO No. 23 - Residential Units ( Level 05-13 ) Additional Walls Missing Information in Residence Tower | 126361.73 |  | 126361.73 |  | Agreed | - | ID/C4242/MZ/5590/18 |  | SBJV issued the Cost Consultant's assessment on 2 Oct 2018 (RAP/SBJ/RSM/2.12.26/18/05444) in the amount of AED 132,679.82 (126,361.73 + 5% for SBJV).
24 | - | VO No.24 - Residential units & Town Houses - Additioinal Walls Missing Information in Residence Tower | 34431 |  | 34430.8 |  | Agreed | 0.2 | ID/C4242/MZ/5619/18 |  | Ishtar accepted the valuation of this VO in the amount of AED 34,430.80 (Excl. 5% for SBJV) in letter ID/C4242/MZ/6419/19. | Amount certified in IPC 65 is as claimed. Appears agreed.
SBJV responded and provided the following:
25 | SOD 2 | Additional Wall Nogging in Hotel Tower | 1202643 | 1202643 |  |  | Not agreed | 1202643 | ID-C4242-ST-5716-18 | 2018-10-02 | Engineer's rejection (Letter 172/PJRC19- 27/DM/SBJ/20/03022); and, | Ishtar did not respond to SBJV's response. | 1202643 | 1202643 | Mr Fitch has done no review of the quantities claimed. He has applied the claimed quantities in his assessment. | Mr Fitch has done no review of the rates claimed. He has applied the claimed rates in his assessment.
Cost Consultant's Nil valuation (Letter RAP/SBJ/DMC/2.12.26/20/14145)
Appendix RER-1-QKC-2.1 - Mr Clarke's assessment summary (Variations)
Summary of all Variations
[5 empty] | Actually in dispute |  |  |  | Paper trail of the variation |  |  |  | Mr Fitch's valuations |  | Mr Clarke comments on Mr Fitch's assessments
VO No. | SD No. | Variation description | Final Claimed Amount | Amount claimed in SOD (AED) | Not certified but agreed by Ishtar | Not confirmed as agreed by Ishtar but certified in IPC 65 | Appears Agreed / Not agreed | Disputed value | Initial Submission, Letter Ref. | Date received by SBJV | SBJV Response | Current status of the VO (i.e who stopped responding) | Mr Fitch's understanding of the claimed amount (AED) | Fitch Assessment Values (AED) | Qty comments | Rate comments
26 | - | VO No. 26 Additional Walls for FHC Residential Corridors & Core Wall.:-Residential -Corridors-Additional wall for FHC- Missing information (L1-L28) AND Residential Units (Level 18-34) -Additional walls missing Information (FHC @ Core B in Residence Tower | 168333.91 |  | 101772.43 |  | Not agreed | 66561.48 | ID/C4242/MZ/5717/19 |  | SBJV issued the Cost Consultant's assessment on 2 Oct 2019 (RAP/SBJ/DBR/2.12.26/19/11852) in the amount of AED 106,861.05 (101,772.43 + 5% for SBJV).
27 | - | VO No. 27 - RMU Architectural & Facade IFC Hotel & Residences in Podium | 268109.52 |  | 268109.57 |  | Agreed | -0.05 | ID/C4242/ST/5744/18 |  | Ishtar accepted the Cost Consultant's assessment in letter ID/C4242/MZ/6596/19 (268,109.57 excl. 5% for SBJV). | Amount certified in IPC 65 is as claimed. Appears agreed.
28 | - | VO#28 Upstand Concrete kerb at louv er doors and windows converted to solid block | 15677.37 |  |  |  | Not agreed | 15677.37 | ID-C4242-ST-5745-18 |  | SBJV responded stating that it is not a variation (RAPSBJ/MAL/2.12.26/18/05699)
29 | - | VO No. 29 Additional Walls for FHC Hotel Corridors & Core Wall in Hotel Tower | 366847.1 |  | 366847.1 |  | Agreed | - | ID/C4242/MZ/5719/19 |  | SBJV issued the Cost Consultant's assessment on 4 June 2020 (RAP/SBJ/FLH/2.12.26/20/16468) in the amount of AED 385,189.46 (366,847.10 + 5% for SBJV).
30 | - | VO No. 30 - Additional Lining Request for Wall Type at Basement in Podium | 14420.73 |  |  |  | Not agreed | 14420.73 | ID/C4242/ST/5746/18 | 2018-10-08 | Unable to determine if SBJV responded to letter ID-C4242-ST-5746-18.
31 | SOD 2 | Additional Wall Nogging for Wall Panelling Installation at Hotel Corridor (L5-8) in Hotel Tower | 47469.6 | 47469.6 |  |  | Not agreed | 47469.6 | ID-C4242-ST-5747-18 |  |  |  | 47469.6 | 34977.6 | Fitch taken as claimed by Ishtar.
32 | - | VO#32 (Upstand Concrete kerb at louv er doors and windows converted to solid block | 14011.22 |  |  |  | Not agreed | 14011.22 | ID-C4242-ST-5812-18 | 2018-10-31 | Unable to determine if SBJV responded to letter ID-C4242-ST-5812-18.
33 | - | VO No. 33 Architectural & Interior Design IFC - Mediterranean Restaurant in Podium | 1083689 |  | 1083689 |  | Agreed | - | ID-C4242-MZ-5873-18 | 2018-11-15 | SBJV issued a SVO (see TRA/SBJ/FLH/2.12.26/20/14614) in the amount of AED 1,083,689 after Ishtar accepted the Cost Consultant's assessment in letter ID/C4242/MZ/6595/19 (without 5% for SBJV).
SBJV responded and provided the following:
34 | SOD 4 | VO No. 34 Additional Sealant for FR Partition in Combined Areas | 3117888 | 3117888 |  |  | Not agreed | 3117888 | ID/C4242/ST/ 5981/18 | 2018-12-26 | Engineer's rejection (Letter 172/PJCR19- 27/DM/SBJ/20/03017 (see letter RAP/SBJ/DMC/2.12.26/20/20287, page 2)); and, | Ishtar did not respond to SBJV's response. | 3117888 | 2232793.53 | Fitch has done no review of the quantities claimed. He applied the claimed quantities in his assessment. | Mr. Fitch has used the rate in the Quotation since the a quotation rate includes supply and apply. He removed wastage, scaffolding & Equipment, Superv ision and OH&P in the rate build up.
Mr. Fitch includes OH&P on his overall assessment
Cost Consultant's Nil valuation (Letter RAP/SBJ/DMC/2.12.26/21/20708)
35 | SOD 2 | VO No. 35 Rectification of Damages caused by Others on the installed Partitions in all areas | 154253.64 | 154253.64 |  |  | Not agreed | 154253.64 | ID/C4242/SO/6060/19 |  |  |  | 154253.64 | - | No Assessment
36 | SOD 4 | VO No. 36 Control Joints in Basement, Lower Ground & Ground Floor | 2988926 | 2988926 |  |  | Not agreed | 2988926 | ID/C4242/JA/6971/19 | 2019-11-13 | Following an RFC raised by Ishtar there was various correspondence before the Engineer rejected Ishtar's VO claim. (see letter RAP/SBJ/DMC/2.12.26/20/20144) | Ishtar did not respond to the Engineer's latest rejection. | 2988926 | 1280860.76 | Fitch has verified the quantities claimed with the marked up drawing provided. Fitch has done no review of the quantites claimed for Labelling. He applied the claimed quantities in his assessment. | Mr. Fitch has provided his rate build up at "CER-1 App VO- 036 Assessment", tabs titled '"Rate Breakdown (Assessed)" and "Unit Breakdown (Assessed)" (a) Rate Breakdown (Assessed) - Mr. Fitch used the rate in the quotation for supply and apply, and removed scaffolding, superv ision, OH&P and Financing Charges. (b) Unit Breakdown (Assessed) - Mr. Fitch calculated the supply and installation of Filler board for 1 square meter. From the quotation, Mr. Fitch has calculated the material rate for 1 square meter in a 1 sheet / 1.2m x 2.4m Filler Board. Mr Fitch has provided his assessment of daywork rates by considering the actual labour cost in ishtar letter ref ID-C4242-ST-5974-18 dated 24 December 2018. Mr. Fitch includes OH&P on his overall assessment
37 | SOD 2 | VO No. 37 Additional Plywood for Hotel Tower Main Doors in Hotel Tower | 265196 | 265196 |  |  | Not agreed | 265196 | ID/C4242/ST/6076/19 |  |  |  | 265196 | 265037.2 | Fitch taken as claimed by Ishtar.
38 | - | VO No. 38 Part 1 Block fair facing- Basement level (Zone 17,19 & 20) Provisional quantities value engineering confirmation for packages F9a & F9b in Podium | 68066.67 |  | 68066.67 |  | Agreed | 0 | ID/C4242/SM/6100/19 |  | SBJV issued the Cost Consultant's assessment on 15 December 2020 (RAP/SBJ/DMC/2.12.26/20/20458) in the amount of AED 71,470 (68,066.67 + 5% for SBJV).
39 | SOD 4 | VO No. 39 Additional Drawings to Incorporate RFIs' & New IFCs' ,Engineering | 416020 | 416020 |  |  | Not agreed | 416020 | ID/C4242/ST/6109/19 | Rev. 03 received 8 July 2020 | SBJV have passed Ishtar's claim on to the Cost Consultant (see Mail Number SBJV- CONPROP-002340) | Have not seen response from Cost Consultant or SBJV passing a Cost Consultant response on to Ishtar. | 416020 | - | Mr Fitch's assessment is zero, subject to providing actual invoices, signed day work sheets to prove execution of the above variations.
40 | - | VO No. 40 Part 1 Re-measurement of Cement Board (Residential Units) in Combined Areas | 549872 |  | 549872.07 |  | Agreed | -0.07 | ID/C4242/MZ/ 6112/19 |  | Ishtar accepted the valuation of this VO in the amount of AED 549,872.07 (Excl. 5% for SBJV) in letter ID/C4242/MZ/7316/20.
41 | - | VO No. 41 Part 1 Updated Design BTU Locations (L01 - L17) Residential Towers | 976127.04 |  | 976127.04 |  | Agreed | - | ID-C4242-SM-6143-19 |  | SBJV issued the Cost Consultant's assessment on 16 Aug 2020 (RAP/SBJ/DMC/2.12.26/20/17932) in the amount of AED 1,024,933.39 (976,127.04 + 5% for SBJV).
42 | - | VO No. 42 EI-P No. 231 Release of IFC Information for Robatayaki Restaurant & Tunnel in Podium | 162833.2 |  | 162833.2 |  | Agreed | - | ID/C4242/MZ/5992/19 |  | SBJV issued the Cost Consultant's assessment on 18 Oct 2020 (RAP/SBJ/DMC/2.12.26/20/19350) in the amount of AED 170,974.86 (162,833.20 + 5% for SBJV).
43 | - | VO No. 43 EI-P No. 475 Architectural IFC Drawings - Food Court (Rev. 01) in Podium | 189486.62 |  | 189486.62 |  | Agreed | - | ID-C4242-MZ-6199-19 |  | Ishtar accepted the valuation of this VO in the amount of AED 189,486.62 (Excl. 5% for SBJV) in letter ID/C4242/ST/6584/19.
44 | - | VO No. 44 Additional Steel Support for the Marble Partition (Part 1) in Podium | 2773187.34 |  | 2773187.62 |  | Agreed | -0.28 | ID-C4242-MZ-6213-19 |  | SBJV issued the Cost Consultant's assessment on 13 Dec 2020 (RAP/SBJ/DMC/2.12.26/20/20402) in the amount of AED 2,911,847 (2,773,187.62 + 5% for SBJV).
45 | SOD 2 | Opening in Gypsum Board Walls in Utility Rooms of Residential Tower - RT2 (L01 to L03), RT3 (L01-L06) for Relocation of Electrical Points in Residence Tower | 12591.5 | 12591.5 |  |  | Not agreed | 12591.5 | ID/C4242/JA/6353/19 |  |  |  | 12591.5 | 11937.06 | Fitch assessed rate breakdown and have removed manhours for Scaffold Inspector (Part of Prelim), revised number of manhours based on Letters provided. Assessment for Materials is with OH&P
Appendix RER-1-QKC-2.1 - Mr Clarke's assessment summary (Variations)
Summary of all Variations
[5 empty] | Actually in dispute |  |  |  | Paper trail of the variation |  |  |  | Mr Fitch's valuations |  | Mr Clarke comments on Mr Fitch's assessments
VO No. | SD No. | Variation description | Final Claimed Amount | Amount claimed in SOD (AED) | Not certified but agreed by Ishtar | Not confirmed as agreed by Ishtar but certified in IPC 65 | Appears Agreed / Not agreed | Disputed value | Initial Submission, Letter Ref. | Date received by SBJV | SBJV Response | Current status of the VO (i.e who stopped responding) | Mr Fitch's understanding of the claimed amount (AED) | Fitch Assessment Values (AED) | Qty comments | Rate comments
46 | - | Vo No. 46 SDIR No 150 Shaft wall construction in Hotel Tower | 505878.36 |  | 505878.1 |  | Agreed | 0.26 | ID-C4242-ST-6529-19 |  | SBJV issued the Cost Consultant's assessment on 7 March 2020 (RAP/SBJ/DMC/2.12.26/20/14874) in the amount of AED 531,172 (505,878.10 + 5% for SBJV). Ishtar accepted the amount of AED 531,172 in letter ID/C4242/ST/7451/20.
47 | SOD 2 | Block Wall Openings Required for LV Tray (Wild Air) for RT1, RT2 & RT3 in Basement Area | 136888.6 | 136888.6 |  |  | Not agreed | 136888.6 | ID-C4242-JA-6401-19 |  |  |  | 136888.6 | 118522.15 | Fitch assessed rates of manpower and materials based on letter/invoices. Assessment for Materials is with OH&P
48 | - | VO #48- Architectural & Interior Design IFC Drawings-Lower Ground Area -9 in Podium (Family Lounge) | 268517 |  | 268517.59 |  | Agreed | -0.59 | ID-C4242-MZ-6405-19 |  | SBJV issued a SVO (see TRA/SBJ/FLH/2.12.26/19/16641) in the amount of AED 268,517.59 (without 5% for SBJV). | Amount certified in IPC 65 is as claimed. Appears agreed.
49 | SOD 2 | VO No. 49 Rectification of Damages caused by Others on the Installed Partitions | 420073.4 | 420073.4 |  |  | Not agreed | 420073.4 | ID/C4242/SA/6646/19 | 2019-06-19 | SBJV have passed on most of the claimed items(those that relate to VO 49) on to the subcontractors alleged to have caused the damages (see letter RAP/SBJ/FLH/2.12.26/19/12790) | Some of the other subcontractors responded, rejecting thedamages claimedagainst them, SBJV forwarded these responses on to Ishtar. Have not seen further responses from Ishtar. | 420073.4 | 184219.67 | Mr. Fitch has not provided any details. | Fitch have provided different rates from Ishtar, but he has not provided details on how he arrived on the said rates. Assessment is with OH&P
50 | - | VO No. 50 Cement Board for Town House in Residence Tower | 57504.03 |  | 57503.81 |  | Agreed | 0.22 | ID-C4242-MZ-6532-19 |  | SBJV issued the Cost Consultant's assessment on 7 Dec 2020 (RAP/SBJ/DMC/2.12.26/20/20327) in the amount of AED 60,379 (57,503.81 + 5% for SBJV).
51 | - | VO No. 51 Sliding door for Town House in Residence Tower | 132704.06 |  | 132704 |  | Agreed | 0.06 | ID-C4242-MZ-6533-19 |  | SBJV issued the Cost Consultant's assessment on 3 March 2020 (RAP/SBJ/DMC/2.12.26/20/14759) in the amount of AED 132,704. Ishtar accepted this amount in letter ID/C4242/ST/7445/20
52 | - | VO No. 52 Peruv ian & British Restaurant in Hotel Tower | 198960.33 |  | 198960.33 |  | Agreed | - | ID-C4242-MZ-6534-19 |  | SBJV issued the Cost Consultant's assessment on 19 Dec 2019 (RAP/SBJ/DMC/2.12.26/19/13318) in the amount of AED 208,908.35 (198,960.33 + 5% for SBJV).
53 | - | VO No. 53 Release of Updated IFC Information for Architectural P211 SPA & ball room in Hotel Podium | 719849.11 |  | 719849.11 |  | Agreed | - | ID-C4242-MZ-6571-19 |  | Ishtar accepted the valuation of this VO in the amount of AED 719,849.11 (Excl. 5% for SBJV) in letter ID/C4242/MZ/7468/20.
54 | - | VO No. 54 Architectural IFC for Spanish & Persian Restaurant in Hotel Podium | 56202.14 |  | 56202.14 |  | Agreed | - | ID-C4242-MZ-6572-19 |  | Ishtar accepted the valuation of this VO in the amount of AED 56,202.14 (Excl. 5% for SBJV) in letter ID/C4242/MZ/6682/19.
55 | - | VO No. 55 Structural & Architectural IFCs - Penthouse 3 | 85565 |  | 85565 |  | Agreed | - | ID-C4242-MZ-6580-19 |  | Ishtar accepted the valuation of this VO in the amount of AED 85,565 (Excl. 5% for SBJV) in letter ID/C4242/MZ/6830/19.
56 | - | VO No. 56 Architectural IFC for Persian Restaurant in Hotel Podium | 28809 |  | 28808.79 |  | Agreed | 0.21 | ID-C4242-MZ-6587-19 |  | Ishtar accepted the valuation of this VO in the amount of AED 28,808.79 (Excl. 5% for SBJV) in letter ID/C4242/MZ/7274/20.
57 | SOD 4 | VO No. 57 Architectural IFC Peruv ian Restaurant in Hotel Tower | 96639.36 | 96639.36 |  |  | Not agreed | 96639.36 | ID-C4242-MZ-6599-19 |  |  |  | 96639.36 | 241065.81 | Fitch taken as claimed by Ishtar. OH&P in New Rates
58 | SOD 4 | VO No. 58 Fire Stopping Application at Partition Interface with Façade | 268313 | 268313 |  |  | Not agreed | 268313 | ID-C4242-JA-6614-19 |  |  |  | 268313 | 2002.08 | Fitch have adapted Ishtar's claim for Labelling and removed claim for Sealant for partition due to no evidence for extra work. assessed rates and qty. Assessment is withot OH&P
59 | - | VO No. 59 : Release of IFC Information to Proceed for Podium | 81390.12 |  | 81390.12 |  | Agreed | - | ID-C4242-MZ-6640-19 |  | Ishtar accepted the valuation of this VO in the amount of AED 81,390.12 (Excl. 5% for SBJV) in letter ID/C4242/MZ/7463/20. | Amount certified in IPC 65 is as claimed. Appears agreed.
60 | SOD 2 | VO NO.60 Rectification of Damages caused on the installed partitions by MEP(Future metro ) - Residential towers | 100169 | 100169 |  |  | Not agreed | 100169 | ID/C4242/SM/6981/19 |  |  |  | 100169 | 69588.44 | Fitch assessed rates and qty. Provided take off-sheet shows only Fitch's assessment. Assessment is with OH&P for Materials
61 | - | VO NO.61 Updated Architectural IFC (Rev 01) for Basement | 14516 |  | 14516 |  | Agreed | - | ID-C4242-MZ-6987-19 |  | Ishtar accepted the valuation of this VO in the amount of AED 14,516 (Excl. 5% for SBJV) in letter ID/C4242/MZ/7183/20. | Amount certified in IPC 65 is as claimed. Appears agreed.
62 | SOD 4 | VO NO.62 Additional works requested by Future metro | 218686 | 218686 |  |  | Not agreed | 218686 | ID-C4242-SM-7024-19 |  |  |  | 218686 | 173434.94 | Fitch assessed rates and qty. Provided take off-sheet shows only Fitch's assessment. Assessment is with OH&P for Materials
63 | - | VO NO.63 Updated Architectural IFC for All Day Dining | 163319 |  | 163318.72 |  | Agreed | 0.28 | ID-C4242-MZ-7062-19 |  | Ishtar accepted the valuation of this VO in the amount of AED 163,318.72 (Excl. 5% for SBJV) in letter ID/C4242/MZ/7662/2020. | Amount certified in IPC 65 is as claimed. Appears agreed.
64 | SOD 2 | VO NO.64 Installation of all recessed Fire Hose Cabinets in Podium (LG & GF) | 575776.21 | 575776.21 |  |  | Not agreed | 575776.21 | ID/C4242/MZ/7065/19 |  |  |  | 575776.21 | - | No Assessment
65 | SOD 2 | VO NO.65 Additional works based on CVI | 221884 | 221884 |  |  | Not agreed | 221884 | ID/C4242/JA/7059/19 |  |  |  | 221884 | 164168.79 | Fitch assessed rates and qty. Provided take off-sheet shows only Fitch's assessment. Assessment is with OH&P for Materials
66 | - | VO NO.66 Architectural IFC for Level 21 to 24 Sky Pool | 376709 |  | 376709 |  | Agreed | - | ID-4242-MZ-7112-19 |  | Ishtar accepted the valuation of this VO in the amount of AED 376,709 (Excl. 5% for SBJV) in letter ID/C4242/MZ/7598/2020.
Appendix RER-1-QKC-2.1 - Mr Clarke's assessment summary (Variations)
Summary of all Variations
[5 empty] | Actually in dispute |  |  |  | Paper trail of the variation |  |  |  | Mr Fitch's valuations |  | Mr Clarke comments on Mr Fitch's assessments
VO No. | SD No. | Variation description | Final Claimed Amount | Amount claimed in SOD (AED) | Not certified but agreed by Ishtar | Not confirmed as agreed by Ishtar but certified in IPC 65 | Appears Agreed / Not agreed | Disputed value | Initial Submission, Letter Ref. | Date received by SBJV | SBJV Response | Current status of the VO (i.e who stopped responding) | Mr Fitch's understanding of the claimed amount (AED) | Fitch Assessment Values (AED) | Qty comments | Rate comments
67 | SOD 2 | Rectification of fire sealant damage caused by MEP subcontractor | 30588 | 30588 |  |  | Not agreed | 30588 | ID/4242/SM/7197/20 |  |  |  | 30588 | - | Assessment is Nil
68 | SOD 4 | VO NO.68 Rectification of Damages caused by Specon | 170322.23 | 170322.23 |  |  | Not agreed | 170322.23 | ID-4242-SM-7273-20 |  |  |  | 170322.23 | 156134.73 | Fitch assessed rates and qty. Provided take off-sheet shows only Fitch's assessment. Assessment is with OH&P for Materials
69 | - | VO NO.69 RAW requested by Al Abbar subcontractor | 22800 |  | 22800 |  | Agreed | - | ID-4242-SM-7278-20 |  | Ishtar accepted the valuation of this VO in the amount of AED 22,800 (Excl. 5% for SBJV) in letter ID/C4242/JA/8708/20.
70 | SOD 4 | VO NO.70 Additional Works requested by III | 32440 | 32440 |  |  | Not agreed | 32440 | ID-C4242-SM-7279-20 |  |  |  | 32440 | 28270 | Fitch taken as claimed by Ishtar w/o profit
71 | SOD 4 | VO NO.71-Damages due to Heavy rain | 202310.85 | 202310.85 |  |  | Not agreed | 202310.85 | ID-C4242-JA-7430-20 |  |  |  | 202310.85 | 183918.95 | Fitch taken as claimed by Ishtar w/o profit NO CER-1 VO-71 on the his submission.
72 | - | VO No. 72 FHC at Residential Core | 182225.71 |  | 182225.68 |  | Agreed | 0.03 | ID-C4242-JA-6621-20 |  | Ishtar accepted the valuation of this VO in the amount of AED 182,225.68 (Excl. 5% for SBJV) in letter ID/C4242/JA/8618/20.
73 | SOD 4 | VO NO.73-RAW requested by Specon Subcontractor | 329616.45 | 329616.45 |  |  | Not agreed | 329616.45 | ID-C4242-SM-7391-20 | 2020-03-01 | SBJV respondedwith a provisional assessment (see RAP/SBJ/FLH/2.12.26/20/19183) | Ishtar responded requesting that SBJV revisit their position. (see ID/C4242/WM/8762/21) Have not seen a response from SBJV. | 329616.45 | 322107 | He has applied the claimed quantities in his assessment. | Mr.Fitch Rate for Manhours is 17 aed/hr for regular hours and overtime instead of 25aed/hour as per agreed Day work rates. Mr. Fitch applied in his assessment the claimed ratesfor Materials and Equipment.
74 | SOD 4 | VO NO.74-Additional Work requested by SBJV | 465691.3 | 465691.3 |  |  | Not agreed | 465691.3 | ID-C4242-JA-7514-20 | 2020-05-28 | SBJV responded with an initial assessment (see RAP/SBJ/FLH/2.12.26/21/20040) | Ishtar responded, noting their disappointment with SBJV's assessment. (see Letter ID/C4242/WM/8636/20) | 465691.3 | 467220.87 | Mr. Fitch's assessment in "CER-1 App VO-074 Assesment", tab titled "Detailed Breakdown", he has utilized quantities on the Daywork sheets (signed only by Ishtar). | Mr. Fitch's assessment for manhour rate in "CER-1 App VO- 074 Assesment", tab titled "Detailed Breakdown", he has used the BOQ Daywork Rates. Mr. Fitch's assessment for material rate in "CER-1 App VO- 074 Assesment", tab titled "Detailed Breakdown", he has applied the claimed rates as the claimed rates are supported by an Quotation / Invoice / Purchase Order. Mr. Fitch 's overall assessment is with OH&P at 10% on Material Cost.
75 | SOD 4 | VO NO.75-Modification of Excessive Structural Opening for door in Core | 244347.99 | 244347.99 |  |  | Not agreed | 244347.99 | ID-C4242-JA-7523-20 |  |  |  | 244347.99 | 222134.54 | Fitch taken as claimed by Ishtar w/o profit
76 | SOD 4 | VO NO.76-Request for additional works by AHK | 61333.67 | 61333.67 |  |  | Not agreed | 61333.67 | ID-C4242-SM-7626-20 |  |  |  | 61333.67 | 59361.4 | Fitch taken as claimed by Ishtar w/o profit
77 | - | VO NO.77-Architectural IFC for Guard House & PRS Gas Station (Architectural IFC Submission) | 37587 |  | 37586.67 |  | Agreed | 0.33 | ID-C4242-MZ-7697-20 |  | SBJV issued the Cost Consultant's assessment on 29 June 2020 (RAP/SBJ/DMC/2.12.26/19/17019) in the amount of AED 39,466 (37,586.67 + 5% for SBJV).
78 | - | VO NO.78- Architectural IFC for Residential Penthouses 1,2 and 2.1 | 74042.71 |  | 74042.71 |  | Agreed | - | ID-C4242-MZ-7729-20 |  | Ishtar accepted the valuation of this VO in the amount of AED 74,042.71 (Excl. 5% for SBJV) in letter ID/C4242/MZ/8651/2020.
79 | SOD 4 | VO NO.79- Rectification of damages against SBJV at Podium | 179397.24 | 179397.24 |  |  | Not agreed | 179397.24 | ID-C4242-SM-7814-20 |  |  |  | 179397.24 | 172788.4 | Fitch taken as claimed by Ishtar w/o profit
80 | - | Variation No.80: EI-P 0607 CIP 1150 - SDIR 150 & FCN 03755- Tower HT1, HT2, HT3, Sub Risers Shaft Wall Construction- Level 21 up to Level 40 | 249531.88 |  | 249531.88 |  | Agreed | - | ID/C4242/SM/7993/20 |  | Ishtar accepted the valuation of this VO in the amount of AED 249,531.88 (Excl. 5% for SBJV) in letter ID/C4242/SM/8222/2020.
81 | SOD 4 | Variation No.81 Additional works requested by SBJV | 512688.11 | 512688.11 |  |  | Not agreed | 512688.11 | ID/C4242/SM/8122/20 | 2020-09-06 | SBJV responded with various comments. Ishtar responded addressing the comments and provided a revised cost summary. | Have not seen a further response from SBJV. | 512688.11 | 392856.85 | Mr. Fitch's assessment in "CER-1 App VO-081 Assessment", tab titled "Assessment", he has utilized the quantities on the daywork sheets (signed by Ishtar) except for the blockworks. He calculated the blockworks quantity based on the drawings attached on the Dayworks sheet. | Mr. Fitch's assessment for manhour rate in "CER-1 App VO- 081 Assessment", tab titled "Assessment", column I-O, he has used the BOQ Daywork Rates. Mr. Fitch's assessment for material rate in "CER-1 App VO- 081 Assessment", tab titled "Assessment", columns P-W, he has applied the claimed rates as the claimed rates are supported by an Quotation / Invoice / Purchase Order. Mr Fitch's assessment for blockworks in CER-1 App VO-081 Assessment", tab titled "Working (Annexure.A)", he has not used the daywork sheet to derive a rate for blockwork instead he has used the BOQ Rate. Mr. Fitch 's overall assessment is with OH&P at 10% on Material Cost.
82 | SOD 4 | Variation No.82 Additional works requested by SPECON | 504305.26 | 504305.26 |  |  | Not agreed | 504305.26 | ID-4242-JA-8123-20 | 2020-09-06 | SBJV responded with various comments. Ishtar responded addressing one commentand reduced their claimed amount. | Have not seen a further response from SBJV. | 504305.26 | 491589.22 | Mr Fitch has done no review of the quantities claimed. He has applied the claimed quantities in his assessment. | Mr Fitch has done no review of the rates claimed. He has applied the claimed rates in his assessment. Mr. Fitch did not valued the 10% claimed OH&P.
83 | SOD 4 | Variation No.83 Additional works requested by SBJV | 297792.92 | 297792.92 |  |  | Not agreed | 297792.92 | ID/C4242/SM/8157/20 |  |  |  | 297792.92 | 278066.3 | Fitch assessed rates and qty. Provided take off-sheet shows only Fitch's assessment. Assessment is with OH&P for Materials
84 | SOD 4 | VO# 84 Additional nogging Ground & LG | 50504 | 50504 |  |  | Not agreed | 50504 | ID/C4242/JA/8183/20 |  |  |  | 50504 | 50504 | Fitch taken as claimed by Ishtar.
85 | SOD 4 | VO#85 Wall Nogging at Hotel Corridor (Level 09-42) | 234367 | 234367 |  |  | Not agreed | 234367 | ID/C4242/MZ/8184/20 |  |  |  | 234367 | 234367 | Fitch taken as claimed by Ishtar.
86 | SOD 4 | VO#86 Rectification of damages caused by SBJV | 1011176.88 | 1011176.88 |  |  | Not agreed | 1011176.88 | ID/C4242/SM/8091/20 | 2020-09-24 | SBJV passed on most of the damages claims to the respective subcontractors. Some contractors responded denying the damages which SBJV passed on to Ishtar. Ishtar denied the rejections by the other subcontractors and requested SBJV to revisit its position. | Have not seen a further response from SBJV. | 1011176.88 | 537912.07 | Mr. Fitch's assessment in "CER-1 App VO-86', tab 'Damages rectification evalutio' for qty., excludes manhours for overtime. Mr. Fitch has applied the claimed quantities for materials in his assessment. | Mr. Fitch's assessment for manhour rate in "CER-1 App VO- 86', tab 'Damages rectification evalutio', used a flat rate of 17aed/hour for all trades, from foreman to helper instead of the BOQ Day work rates. On rates for materials, Mr.Fitch have applied what is the claimed rates, except for rates that is without provided substantiation.
Appendix RER-1-QKC-2.1 - Mr Clarke's assessment summary (Variations)
Summary of all Variations
[5 empty] | Actually in dispute |  |  |  | Paper trail of the variation |  |  |  | Mr Fitch's valuations |  | Mr Clarke comments on Mr Fitch's assessments
VO No. | SD No. | Variation description | Final Claimed Amount | Amount claimed in SOD (AED) | Not certified but agreed by Ishtar | Not confirmed as agreed by Ishtar but certified in IPC 65 | Appears Agreed / Not agreed | Disputed value | Initial Submission, Letter Ref. | Date received by SBJV | SBJV Response | Current status of the VO (i.e who stopped responding) | Mr Fitch's understanding of the claimed amount (AED) | Fitch Assessment Values (AED) | Qty comments | Rate comments
87 | SOD 4 | VO#87 Bulkhead for Cantilever Suites (Partition's Termination) | 4774499 | 4774499 |  |  | Not agreed | 4774499 | ID/C4242/MZ/8200/20 | 2020-09-23 | SBJV responded (RAP/SBJ/FLH/2.12.26/20/19182) asking Ishtar to raise an RFC and provide additional substantiation. | Have not seen a further response from Ishtar. | 4774499 | 2507367.28 | Fitch has done no review of the quantities claimed. He applied the claimed quantities in his assessment. | Mr. Fitch does not assess the addition rate claimed. Rather, he provides his own rate build up at 'CER-1 App VO-087 Assesment, tab titled 'FitchAssessment Rate Break down' Mr Fitch's rate build up is derived from 1 Lm of bulkhead (fire rated and non fire rated) based on Cantilever Suite Typical Bulkhead Details Drawing "Drawing ref TRA-ISH- SDG-PO-GEN-47900 Rev 03". (a) Material - Mr. Fitch has considered material rate from the PO enclosed in the SBJV Contra Charge letter ref RAP/SBJ/FLH/2.12.26/20/15366 and 10% of Material Cost for OH&P. (b) Labour - Mr Fitch calculated a 1 LM labour rate based on unsigned daywork sheets for the installation of 52 LM bulkhead. (c) Plant & Equipment/Tools - Mr. Fitch has provided a lump sum cost that is 10% of Material Cost. Omission is considered to be based on the BOQ Rates.
88 | - | VO No. 88 Additional Steel Support for the Marble Partition (Part 02) in Podium | 1370321.26 |  | 1370321.26 |  | Agreed | - | ID/C4242/MZ/8300/20 |  | Ishtar accepted the valuation of this VO in the amount of AED 1,370,321.26 (Excl. 5% for SBJV) in letter ID/C4242/MZ/8678/2020.
89 | SOD 4 | VO No. 89 Additional works related to RFI for C6 Package – Part 1 | 87361.72 | 87361.72 |  |  | Not agreed | 87361.72 | ID/C4242/MH/8341/20 |  |  |  | 87361.72 | 87361.72 | Fitch taken as claimed by Ishtar.
90 | SOD 4 | VO No. 90 CIP 2258 Door Nib | 34459.95 | 34459.95 |  |  | Not agreed | 34459.95 | ID/C4242/SM/8325/20 |  |  |  | 34459.95 | 34459.95 | Fitch taken as claimed by Ishtar.
91 | SOD 4 | VO No. 91 BTU level 18 and above -SDIR NO. 49 | 281823.59 | 281823.59 |  |  | Not agreed | 281823.59 | ID/C4242/SM/8364/20 |  |  |  | 281823.59 | - | Assessed as Nil, awaiting Ishtar to provide documents that works has been executed on site.
92 | - | VO No. 92 Robatayaki Restaurant Architectural and BOH (F9) Updated Drawings (Additional Work) | 5817.25 |  | 5817.25 |  | Agreed | 0 | ID/C4242/MZ/8391/20 |  | Ishtar accepted the valuation of this VO in the amount of AED 5,817.25 (Excl. 5% for SBJV) in letter ID/C4242/MZ/8539/2020.
93 | SOD 4 | VO No. 93 Facade Termination-Hotel towers | 2026936.38 | 2026936.38 |  |  | Not agreed | 2026936.38 | ID/C4242/JA/8374/20 | 2020-10-25 | SBJV responded with reasons for its rejection of this VO claim (RAP/SBJV/BPA/2.12.26-20/18738). Ishtar then submitted a detailed breakdown of its claim (ID/C4242/JA/8374/20) SBJV then repeated its rejection (TRA/SBJV/FLH/2.12.26/20/19539) | Have not seen that Ishtar has responded to SBJV's latest rejection. | 2026936.38 | 1785804.8 | Mr Fitch has done no review of the quantities claimed. He has applied the claimed quantities in his assessment. | Mr Fitch does not assess the rates claimed. Rather, he provides his own rate build up at 'CER-1 App VO-93, tab titled 'Analysis'. The rate is built up with two different lengths and a height of 8m to derive a m2. An amount of AED 80 is applied to the m2 with a further 30% uplift applied. Mr Fitch's rate does not include OH&P.
94 | SOD 4 | VO No. 94 Additional works related to RFI for C6 Package – Part 2 | 7699 | 7699 |  |  | Not agreed | 7699 | ID/C4242/MH/8400/20 |  |  |  | 7699 | 111761 | Fitch assessed rates and qty. Measurement/Take off sheet provided is as per Fitch Assessment only. NO OH&P included.
95 | SOD 4 | VO#95 Gas Pipes Shaft walls at Podium & Hotel Towers CIP 2303 | 43782.63 | 43782.63 |  |  | Not agreed | 43782.63 | ID/C4242/MH/8420/20 |  |  |  | 43782.63 | 43782.63 | Fitch taken as claimed by Ishtar.
96 | SOD 4 | VO#96 Wall Demolishing Works Related to RFI 07658 for C6 Package | 13631 | 13631 |  |  | Not agreed | 13631 | ID/C4242/MH/8462/20 |  |  |  | 13631 | 11853.33 | Fitch taken as claimed by Ishtar without OH&P and Processing Cost
97 | SOD 4 | VO#97 Block Walls Demolition Related to RFI 06365 for C6 Package | 20879.63 | 7380 |  |  | Not agreed | 20879.63 | ID/C4242/MH/8463/20 |  |  |  | 20879.63 | 18156.2 | Fitch taken as claimed by Ishtar without OH&P and Processing Cost
98 | SOD 4 | VO#98 Walls Tags Missing Information for C6 Package | 102815 | 102815 |  |  | Not agreed | 102815 | ID/C4242/MH/8464/20 |  |  |  | 102815 | 93468.49 | Fitch taken as claimed by Ishtar without OH&P and Processing Cost
99 | SOD 4 | VO#99 Residential unit (3 BED TYPE 8) - kitchen Wall type Changed Related to RFI 05018 | 6202 | 6202 |  |  | Not agreed | 6202 | ID/C4242/MH/8465/20 |  |  |  | 6202 | 5393.02 | Fitch taken as claimed by Ishtar without OH&P and Processing Cost
100 | SOD 4 | VO#100 Additional Walls for Dewa HV Cables Related to RFI 05843 | 13004 | 13004 |  |  | Not agreed | 13004 | ID/C4242/MH/8466/20 |  |  |  | 13004 | 11307.66 | Fitch taken as claimed by Ishtar without OH&P and Processing Cost
101 | SOD 4 | VO#101 Wall Type Changed for Hotel suit Level 41 and 42 Related to RFI 06856 | 3600 | 3600 |  |  | Not agreed | 3600 | ID/C4242/MH/8467/20 |  |  |  | 3600 | 3130.11 | Fitch taken as claimed by Ishtar without OH&P and Processing Cost
102 | SOD 4 | VO#102 Wall Type Changed Lower Ground Floor Zone 17 Related to RFI 07327 | 8210 | 8210 |  |  | Not agreed | 8210 | ID/C4242/MH/8477/20 |  |  |  | 8210 | 7139.22 | Fitch taken as claimed by Ishtar without OH&P and Processing Cost
103 | SOD 4 | VO#103 Additional Masonry Wall at Basement Zone 16 (DEC Letter 02465) | 34183 | 34183 |  |  | Not agreed | 34183 | ID-C4242-MH-8503-20 |  |  |  | 34183 | 29724.7 | Fitch taken as claimed by Ishtar without OH&P and Processing Cost
104 | SOD 4 | VO#104 Alight Access Platform - Duct Rerouting SDIR 0330 | 3703 | 39730 |  |  | Not agreed | 3703 | ID-C4242-MH-8552-20 |  |  |  | 3703 | 11722.32 | Fitch removed additional cost for demolition works and adapted cost for additional wall without OH&P
105 | SOD 4 | VO#105 Protection for MEP Services Proposed for BOH Areas-EIP 0837 | 89310 | 89310 |  |  | Not agreed | 89310 | ID-C4242-MH-8553-20 |  |  |  | 89310 | 84235.3 | Fitch Adapted cost for Additional Masonry Wall. For Additional Manhours and Additional Equipment, he provided different rate, however did not indicate how he arrived on that rate.
106 | SOD 4 | 106.VO#106 Additional Walls at 22nd floor - Zone 03 - Related to DEC L 02551 | 17859 | 17859 |  |  | Not agreed | 17859 | ID-C4242-MH-8554-20 |  |  |  | 17859 | 17082.29 | Fitch taken as claimed by Ishtar without OH&P and Processing Cost
107 | SOD 4 | 107.VO#107 Additional Walls at Third Floor Zone 04 - Related to DEC L 02076 | 42233 | 42233 |  |  | Not agreed | 42233 | ID-C4242-MH-8599-20 |  |  |  | 42233 | 36724.65 | Fitch taken as claimed by Ishtar without OH&P and Processing Cost
108 | SOD 4 | VO#108 Wall Nogging at Podium Level 2 | 24960 | 24960 |  |  | Not agreed | 24960 | ID-C4242-MH-8619-20 |  |  |  | 24960 | 23874.92 | Fitch taken as claimed by Ishtar without Processing Cost
109 | SOD 4 | VO No.109: Additional Walls at Mediterranean restaurant - Second Floor- related to DEC letter 02567 | 19093 | 19093 |  |  | Not agreed | 19093 | ID/C4242/MH/8637/20 |  |  |  | 19093 | 16602.25 | Fitch taken as claimed by Ishtar without OH&P and Processing Cost
110 | - | WHAT IS VO |  |  | N/A |  | N/A | N/A | ` | N/A | N/A | N/A
111 | SOD 4 | VO#111- Façade Termination at Residential Tower | 1753661.48 | 1753661.48 |  |  | Not agreed | 1753661.48 | ID/C4242/JA/8683/20 | 2020-12-20 | SBJV responded with reasons for its rejection of this VO claim (RAP/SBJV/BPA/2.12.26-20/18738). Ishtar then submitted a detailed breakdown of its claim (ID/C4242/JA/8683/20) SBJV then repeated its rejection (TRA/SBJV/FLH/2.12.26/20/20425) | Have not seen that Ishtar has responded to SBJV's latest rejection. | 1753661.48 | 1151504.64 | Mr Fitch has done no review of the quantities claimed. He has applied the claimed quantities in his assessment. | Mr Fitch does not assess the rates claimed. Rather, he provides his own rate build-up at 'CER-1 App VO-111, tab titled 'Analysis'. The rate is built up with a length and a height of 8m to derive a m2. An amount of AED 80 is applied to the m2 with a further 30% uplift applied. Mr Fitch's rate does not include OH&P, However total assessment has 10% OH&P.
112 | SOD 4 | VO#112 Façade Support Wall [Steel Wind Post for 200mm thick block wall (Provisional)] | 1260247.97 | 1260247.97 |  |  | Not agreed | 1260247.97 | ID/C4242/MZ/8706/20 | 2020-12-22 | I have not seen any response from SBJV to Ishtar's claims |  | 1260247.97 | 1260247.97 | Mr Fitch has done no review of the quantities claimed. He has applied the claimed quantities in his assessment. | Mr Fitch has done no review of the rates claimed. He has applied the claimed rates in his assessment.
113 | SOD 4 | VO#113 EIPL 0835-EIP 0782- Mediterranean Restaurant FHC | 21417 | 21417 |  |  | Not agreed | 21417 | ID/C4242/MZ/8722/20 |  |  |  | 21417 | 21417 | Fitch taken as claimed by Ishtar.
114 | SOD 4 | VO#114 Additional Walls in Basement Zone 06 - DEC 00646 | 22075 | 22075 |  |  | Not agreed | 22075 | ID-C4242-MH-8679-21 |  |  |  | 22075 | 22075.36 | Fitch taken as claimed by Ishtar.
115 | SOD 4 | VO#115 Additional Walls at Basement Zone 02 - DEC 00840 | 5421 | 5421 |  |  | Not agreed | 5421 | ID-C4242-MH-8680-21 |  |  |  | 5421 | 5420.65 | Fitch taken as claimed by Ishtar.
116 | SOD 4 | VO#116 - CIP 1124 /EIP 0602 Architectural IFC Drawings - Bridge Suite | 29502 | 29502 |  |  | Not agreed | 29502 | ID/C4242/MZ/8813/21 |  |  |  | 29502 | 29502 | Fitch taken as claimed by Ishtar.
Appendix RER-1-QKC-2.1 - Mr Clarke's assessment summary (Variations)
Summary of all Variations
[5 empty] | Actually in dispute |  |  |  | Paper trail of the variation |  |  |  | Mr Fitch's valuations |  | Mr Clarke comments on Mr Fitch's assessments
VO No. | SD No. | Variation description | Final Claimed Amount | Amount claimed in SOD (AED) | Not certified but agreed by Ishtar | Not confirmed as agreed by Ishtar but certified in IPC 65 | Appears Agreed / Not agreed | Disputed value | Initial Submission, Letter Ref. | Date received by SBJV | SBJV Response | Current status of the VO (i.e who stopped responding) | Mr Fitch's understanding of the claimed amount (AED) | Fitch Assessment Values (AED) | Qty comments | Rate comments
117 | SOD 4 | VO#117 Additional Embraced Walls - RFI 04937 | 774261 | 774261 |  |  | Not agreed | 774261 | ID/C4242/MH/8818/21 | No received stamp from SBJV. | SBJV responded and requested Ishtar to provide a RFC in relation to TRA/SBJ/RFI/PO/GEN/04937 Rev. 01 (see Letter TRA/SBJ/FLH/2.12.26/21/21140) | Have not seen a further response from Ishtar. | 774261 | 169509.83 | Mr.Fitch assessment for quantities only include quantities for wall partition 1.6 and 1.6u. He applied the claimed quantities in his assessment. | Mr.Fitch assessment for rates only include rates for wall partition 1.6 and 1.6u. He applied the claimed rates in his assessment. Rates is inclusiv e of 10% OH&P
118 | SOD 4 | VO#118 - CIP No. 2180 / EIP 0990 New WET Workshop- Basement Plan Area 11 rev (Mediterranean Restaurant) | 95425.79 | 95425.79 |  |  | Not agreed | 95425.79 | ID/C4242/MZ/8879/21 |  |  |  | 95425.79 | 95425.79 | Fitch taken as claimed by Ishtar.
119 | SOD 4 | VO#119 Additional Walls at Residential Tower - DEC 00655 | 4713.14 | 4713.14 |  |  | Not agreed | 4713.14 | ID-C4242-MH-8830-21 |  |  |  | 4713.14 | 4713.14 | Fitch taken as claimed by Ishtar.
120 | SOD 4 | VO#120 Additional Walls at Mediterranean Restaurant Ground Floor - RFI 09315 | 9493 | 9493 |  |  | Not agreed | 9493 | ID-C4242-MH-8881-21 |  |  |  | 9493 | 9492.89 | Fitch taken as claimed by Ishtar.
121 | SOD 4 | VO#121 Additional Niche at Hotel & Residential Towers Bathroom - RFI 10703 & RFI 08105 | 165829.5 | 165829.5 |  |  | Not agreed | 165829.5 | ID-C4242-MH-8862-21 |  |  |  | 165829.5 | 165829.5 | Fitch taken as claimed by Ishtar.
122 | SOD 4 | VO#122 - Mediterranean LG / GF - Missing Wall Tags / Discrepancy with ID | 10663.97 | 10663.97 |  |  | Not agreed | 10663.97 | ID/C4242/MZ/8898/21 |  |  |  | 10663.97 | 10663.97 | Fitch taken as claimed by Ishtar.
123 | SOD 4 | VO#123 Super Penthouse Service Elevator Shaft Enclosure | 15250.25 | 15250.25 |  |  | Not agreed | 15250.25 | ID/C4242/MZ/8907/21 |  |  |  | 15250.25 | 15250.25 | Fitch taken as claimed by Ishtar.
124 | SOD 4 | VO#124 Additional Cement Board @ Ground Floor RFC 00625(RFI 13538) | 5264.58 | 38521.52 |  |  | Not agreed | 5264.58 | ID/C4242/MZ/8954/21 |  | Ishtar accepted the valuation of this VO in the amount of AED 5,264.58 (Excl. 5% for SBJV) in letter ID/C4242/MZ/9184/2021. |  | 5264.58 | 8392.84 | Fitch taken as claimed by Ishtar.
125 | - | VO#125 Cake and Ice Cream Shops Works - TIME-PM-ADV- 000907 | 37980.89 |  | 37980.89 |  | Agreed | - | ID/C4242/MZ/8954/21 |  | Ishtar accepted the valuation of this VO in the amount of AED 37,980.89 (Excl. 5% for SBJV) in letter ID/C4242/MZ/9127/2021.
126 | SOD 4 | Vo #126 Request for Additional works requested by SBJV and its subcontractors | 691851 | 691851 |  |  | Not agreed | 691851 | ID-C4242-MH-8958-21 | 2021-02-23 | SBJV responded with a preliminary review of Ishtar's claim, including various comments. (see Letter RAP/SBJ/FLH/2.12.26/21/21849) | Have not seen a further response from Ishtar. | 691851 | 761982.88 | Mr.Fitch assessed his quantities by checking the Day Work Sheet (signed by Ishtar). All Surveyor that is claimed under Manhours he exclued as he categorized it as site superv ision and cannot be considered. | For his assessment of rates in manhours, Mr.Fitch used the BOQ rate of 25/hour for both regular hours and overtime hours. For His Assessment for Materials and Plant and Equipment, he applied the claimed rates however there are instance s where he have corrected the rates as per as per PO, and letter reference that the Claimant reffered for the rates. He Applied OH&P of 10% for Materials and PLant & Equipment.
127 | SOD 4 | Vo #127 Request for Additional works requested by SBJV and its subcontractors | 196016 | 196016 |  |  | Not agreed | 196016 | ID-C4242-MH-8975-21 |  |  |  | 196016 | 145839.25 | Fitch assessed qty and rates, provided revised worksheet with Fitch Assessment only. Assessment with OH&P
128 | - | VO#128 - Mediterranean Restaurant- Missing Block/Partitions- TIME-PM-ADV-000956 & 000965 | 49630 |  | 49630 |  | Agreed | - | ID/C4242/MZ/8994/21 |  | Ishtar accepted the valuation of this VO in the amount of AED 49,630 (Excl. 5% for SBJV) in letter ID/C4242/MZ/9305/2021.
129 | - | VO#129 Release of Updated IFC Lower Ground Zone 19 - DEC Letter 03014 | 3397 |  | 3397 |  | Agreed | - | ID-C4242-MH-9070-21 |  | Ishtar accepted the valuation of this VO in the amount of AED 3,397 (Excl. 5% for SBJV) in letter ID/C4242/MZ/9359/2021.
130 | - | VO#130 Spa Lap Pool & Spanish Water Feature Plantroom Updated Drawings – IFC Submission (Basement Zone 16, DEC Letter 03303) | 10652 |  | 10652 |  | Agreed | - | ID-C4242-MH-9125-21 |  | Ishtar accepted the valuation of this VO in the amount of AED 10,652 (Excl. 5% for SBJV) in letter ID/C4242/MZ/9185/2021.
131 | - | VO#131 Additional Dry Wall Partition at HT1 Level 44 | 76346 |  |  |  | Not agreed | 76346 | ID/C4242/MZ/9157/21 | 2021-04-10 | Unable to lacate a response to this letter from SBJV.
132 | - | VO#132 Modification of Relocating the CRAC Units for the Hotel at Beasement Zone 07 & 17 | 9181 |  | 9181 |  | Agreed | - | ID/C4242/MZ/9182/21 |  | Ishtar accepted the valuation of this VO in the amount of AED 9,181 (Excl. 5% for SBJV) in letter ID/C4242/MZ/9259/2021.
133 | - | VO#133 -C6-Additional Cement Board at Hotel Level 22 Locker Room | 5495.7 |  |  |  | Not agreed | 5495.7 | ID/C4242/MZ/9203/21 | 2021-04-24 | Unable to lacate a response to this letter from SBJV.
134 | - | VO#134-L29 Sky Court Revised IFC Submission | 29606 |  | 29606 |  | Agreed | - | ID/C4242/MZ/9244/21 |  | Ishtar accepted the valuation of this VO in the amount of AED 29,606 (Excl. 5% for SBJV) in letter ID/C4242/MZ/9295/2021.
135 | - | VO#135- L29 Skycourt Wash Room Finishes RFI#14333 | 6583.4 |  |  |  | Not agreed | -6583.4 | ID/C4242/MZ/9245/21 | 2021-07-05 | Unable to lacate a response to this letter from SBJV.
136 | - | VO#136 Additional partition required for Weather tightness of Building Envelope @ RT3 L39-40 | 57753 |  | 55848 |  | Agreed | -1905 | ID/C4242/MZ/9274/21 |  | Ishtar accepted the valuation of this VO in the amount of AED 55,848 (Excl. 5% for SBJV) in letter ID/C4242/MZ/9516/2021.
137 | SOD 7 | THIS IS A CC VARIATION | 1047317.09 | 1047317.09 |  |  | Not agreed | 1047317.09 |  |  |  |  | 1047317.09 | 99310 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
138 | SOD 7 | THIS IS A CC VARIATION | 1993058.15 | 1993058.15 |  |  | Not agreed | 1993058.15 |  |  |  |  | 1993058.15 | 114385 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
139 | SOD 7 | THIS IS A CC VARIATION | 3358288.18 | 3358288.18 |  |  | Not agreed | 3358288.18 |  |  |  |  | 3358288.18 | 193048 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
Appendix RER-1-QKC-2.1 - Mr Clarke's assessment summary (Variations)
Summary of all Variations
[5 empty] | Actually in dispute |  |  |  | Paper trail of the variation |  |  |  | Mr Fitch's valuations |  | Mr Clarke comments on Mr Fitch's assessments
VO No. | SD No. | Variation description | Final Claimed Amount | Amount claimed in SOD (AED) | Not certified but agreed by Ishtar | Not confirmed as agreed by Ishtar but certified in IPC 65 | Appears Agreed / Not agreed | Disputed value | Initial Submission, Letter Ref. | Date received by SBJV | SBJV Response | Current status of the VO (i.e who stopped responding) | Mr Fitch's understanding of the claimed amount (AED) | Fitch Assessment Values (AED) | Qty comments | Rate comments
140 | SOD 7 | THIS IS A CC VARIATION | 1384829.81 | 1384829.81 |  |  | Not agreed | 1384829.81 |  |  |  |  | 1384829.81 | 78315 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
141 | SOD 7 | THIS IS A CC VARIATION | 1170600.6 | 1170600.6 |  |  | Not agreed | 1170600.6 |  |  |  |  | 1170600.6 | 68187 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
142 | SOD 7 | THIS IS A CC VARIATION | 780624.05 | 780624.05 |  |  | Not agreed | 780624.05 |  |  |  |  | 780624.05 | 70256 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
143 | SOD 7 | THIS IS A CC VARIATION | 475319.65 | 475319.65 |  |  | Not agreed | 475319.65 |  |  |  |  | 475319.65 | 132265 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
144 | SOD 7 | THIS IS A CC VARIATION | 507325.24 | 507325.24 |  |  | Not agreed | 507325.24 |  |  |  |  | 507325.24 | 16775 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
145 | SOD 7 | THIS IS A CC VARIATION | 5651614.06 | 5651614.06 |  |  | Not agreed | 5651614.06 |  |  |  |  | 5651614.06 | 353701 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
146 | SOD 7 | THIS IS A CC VARIATION | 3772988.74 | 3772988.74 |  |  | Not agreed | 3772988.74 |  |  |  |  | 3772988.74 | 353701 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
147 | SOD 7 | THIS IS A CC VARIATION | 5255316.61 | 5255316.61 |  |  | Not agreed | 5255316.61 |  |  |  |  | 5255316.61 | 286723 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
148 | SOD 7 | THIS IS A CC VARIATION | 4917926.79 | 4917926.79 |  |  | Not agreed | 4917926.79 |  |  |  |  | 4917926.79 | 294068 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
149 | SOD 7 | THIS IS A CC VARIATION | 3888770.33 | 3888770.33 |  |  | Not agreed | 3888770.33 |  |  |  |  | 3888770.33 | 225693.95 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
150 | SOD 7 | THIS IS A CC VARIATION | 3204051.23 | 3204051.23 |  |  | Not agreed | 3204051.23 |  |  |  |  | 3204051.23 | 189372.95 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).

## Table 2
[5 empty] | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T
[7 empty] | Actually in dispute |  |  |  |  | Paper trail of the variation |  |  |  |  | Mr Fitch's valuations |  | Mr Clarke comments on Mr Fitch's assessments
[5 empty] | Amount claimed in SOD (AED) |  | Not certified but agreed by Ishtar | Not confirmed as agreed by Ishtar but certified in IPC 65 | Appears Agreed / Not agreed | Disputed value |  | Initial Submission, Letter Ref. | Date received by SBJV | SBJV Response | Current status of the VO (i.e who stopped responding) |  | Mr Fitch's understanding of the claimed amount (AED) | Fitch Assessment Values (AED) | Qty comments | Rate comments
[5 empty] | 6018368.26 |  |  |  | Not agreed | 6018368.26 | [6 empty] | 6018368.26 | 363813.33 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
[5 empty] | 4123373.22 |  |  |  | Not agreed | 4123373.22 | [6 empty] | 4123373.22 | 249419.13 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
[7 empty] | 57730 |  | Not agreed | -56985.08 |  | ID/C4242/MZ/9334/21 | 2021-06-03 | SBJV issued a Rev.02 assessment on 26 July 2021 via letter RAP/SBJ/FLH/2.12.26/21/24001 in the amount of AED 57,730.
164 | 154 | SOD 7 | THIS IS A CC VARIATION | 3568889.27 | E: 3568889.27; I: Not agreed; J: 3568889.27; Q: 3568889.27; R: 208582.87; S: Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
165 | 155 | SOD 7 | THIS IS A CC VARIATION | 4151142.38 | E: 4151142.38; I: Not agreed; J: 4151142.38; Q: 4151142.38; R: 240636.24; S: Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
166 | 156 | - | DEC 03578 Changes in Basement (Area 16 & 19) Updated Architectural Drawings and MEP Sketches | 27835 | G: 27293; I: Agreed; J: 542; L: ID/C4242/MZ/9501/21; M: 2021-09-06; N: Ishtar accepted the valuation of this VO in the amount of AED 27,293.00 (Excl. 5% for SBJV) in letter ID/C4242/MZ/9538/2021.
167 | 157 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 3257888.78 | I: Not agreed; J: 3257888.78
168 | 158 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 4175985.74 | I: Not agreed; J: 4175985.74
169 | 159 | - | Penthouse 3501 - CHW provision to L36 Pool Plant room | 7251 | G: 7252; I: Agreed; J: -1; L: ID/C4242/MZ/9697/21; M: 2021-11-30; N: Ishtar accepted the valuation of this VO in the amount of AED 7,252.00 (Excl. 5% for SBJV) in letter ID/C4242/MZ/9749/2022.
170 | 160 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 5335740.34 | I: Not agreed; J: 5335740.34
171 | 161 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 5671204.37 | I: Not agreed; J: 5671204.37
172 | 162 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 2393234.07 | I: Not agreed; J: 2393234.07
173 | 163 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 1184750.21 | I: Not agreed; J: 1184750.21
174 | 164 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 624208.92 | I: Not agreed; J: 624208.92
175 | 165 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 438730.74 | I: Not agreed; J: 438730.74
176 | 166 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 579781.12 | I: Not agreed; J: 579781.12
177 | 167 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 624396.67 | I: Not agreed; J: 624396.67
178 | 168 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 756285.19 | I: Not agreed; J: 756285.19
179 | 169 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 1180879.8 | I: Not agreed; J: 1180879.8
180 | 170 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 576442.15 | I: Not agreed; J: 576442.15
181 | 171 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 466773.08 | I: Not agreed; J: 466773.08
182 | 172 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 86353.81 | I: Not agreed; J: 86353.81
183 | 173 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 72539.51 | I: Not agreed; J: 72539.51
184 | 174 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 98481.68 | I: Not agreed; J: 98481.68
185 | PS | - | Value Engineering | 900000 | H: 900000; I: Agreed; J: -
186
187 |  |  |  | 127750701.19 | E: 85260354.59; G: 13540715.5; H: 1133209.52; J: 112915112.71
188
189
190

## Table 3
[5 empty] | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U
[7 empty] | Actually in dispute |  |  |  |  | Paper trail of the variation | [5 empty] | Mr Fitch's valuations |  | Mr Clarke comments on Mr Fitch's assessments
[5 empty] | Amount claimed in SOD (AED) |  | Not certified but agreed by Ishtar | Not confirmed as agreed by Ishtar but certified in IPC 65 | Appears Agreed / Not agreed | Disputed value |  | Initial Submission, Letter Ref. | Date received by SBJV | SBJV Response | Current status of the VO (i.e who stopped responding) | Query for SBJV |  | Mr Fitch's understanding of the claimed amount (AED) | Fitch Assessment Values (AED) | Qty comments | Rate comments
10 | 83 | SOD 4 | Variation No.83 Additional works requested by SBJV | 297792.92 | E: 297792.92; I: Not agreed; J: 297792.92; L: ID/C4242/SM/8157/20; R: 297792.92; S: 278066.3; T: Fitch assessed rates and qty. Provided take off-sheet shows only Fitch's assessment. Assessment is with OH&P for Materials
11 | 13 | SOD 2 | Additional Drawings to Incorporate MEP Requirements in Engineering | 296887 | E: 296887; I: Not agreed; J: 296887; L: ID/C4242/ST/5497/18; R: 296887; S: 372527; T: Fitch taken as claimed by Ishtar.
12 | 91 | SOD 4 | VO No. 91 BTU level 18 and above -SDIR NO. 49 | 281823.59 | E: 281823.59; I: Not agreed; J: 281823.59; L: ID/C4242/SM/8364/20; R: 281823.59; S: -; T: Assessed as Nil, awaiting Ishtar to provide documents that works has been executed on site.
13 | 58 | SOD 4 | VO No. 58 Fire Stopping Application at Partition Interface with Façade | 268313 | E: 268313; I: Not agreed; J: 268313; L: ID-C4242-JA-6614-19; O: Amount certified in IPC 65 is as claimed. Appears agreed.; R: 268313; S: 2002.08; T: Fitch have adapted Ishtar's claim for Labelling and removed claim for Sealant for partition due to no evidence for extra work. assessed rates and qty. Assessment is withot OH&P
14 | 37 | SOD 2 | VO No. 37 Additional Plywood for Hotel Tower Main Doors in Hotel Tower | 265196 | E: 265196; I: Not agreed; J: 265196; L: ID/C4242/ST/6076/19; R: 265196; S: 265037.2; T: Fitch taken as claimed by Ishtar.
15 | 75 | SOD 4 | VO NO.75-Modification of Excessive Structural Opening for door in Core | 244347.99 | E: 244347.99; I: Not agreed; J: 244347.99; L: ID-C4242-JA-7523-20; O: Amount certified in IPC 65 is as claimed. Appears agreed.; R: 244347.99; S: 222134.54; T: Fitch taken as claimed by Ishtar w/o profit
16 | 85 | SOD 4 | VO#85 Wall Nogging at Hotel Corridor (Level 09-42) | 234367 | E: 234367; I: Not agreed; J: 234367; L: ID/C4242/MZ/8184/20; R: 234367; S: 234367; T: Fitch taken as claimed by Ishtar.
17 | 65 | SOD 2 | VO NO.65 Additional works based on CVI | 221884 | E: 221884; I: Not agreed; J: 221884; L: ID/C4242/JA/7059/19; O: Amount certified in IPC 65 is as claimed. Appears agreed.; R: 221884; S: 164168.79; T: Fitch assessed rates and qty. Provided take off-sheet shows only Fitch's assessment. Assessment is with OH&P for Materials
18 | 62 | SOD 4 | VO NO.62 Additional works requested by Future metro | 218686 | E: 218686; I: Not agreed; J: 218686; L: ID-C4242-SM-7024-19; R: 218686; S: 173434.94; T: Fitch assessed rates and qty. Provided take off-sheet shows only Fitch's assessment. Assessment is with OH&P for Materials
19 | 71 | SOD 4 | VO NO.71-Damages due to Heavy rain | 202310.85 | E: 202310.85; I: Not agreed; J: 202310.85; L: ID-C4242-JA-7430-20; R: 202310.85; S: 183918.95; T: Fitch taken as claimed by Ishtar w/o profit NO CER-1 VO-71 on the his submission.
20 | 127 | SOD 4 | Vo #127 Request for Additional works requested by SBJV and its subcontractors | 196016 | E: 196016; I: Not agreed; J: 196016; L: ID-C4242-MH-8975-21; R: 196016; S: 145839.25; T: Fitch assessed qty and rates, provided revised worksheet with Fitch Assessment only. Assessment with OH&P
21 | 79 | SOD 4 | VO NO.79- Rectification of damages against SBJV at Podium | 179397.24 | E: 179397.24; I: Not agreed; J: 179397.24; L: ID-C4242-SM-7814-20; R: 179397.24; S: 172788.4; T: Fitch taken as claimed by Ishtar w/o profit
22 | 68 | SOD 4 | VO NO.68 Rectification of Damages caused by Specon | 170322.23 | E: 170322.23; I: Not agreed; J: 170322.23; L: ID-4242-SM-7273-20; R: 170322.23; S: 156134.73; T: Fitch assessed rates and qty. Provided take off-sheet shows only Fitch's assessment. Assessment is with OH&P for Materials
23 | 121 | SOD 4 | VO#121 Additional Niche at Hotel & Residential Towers Bathroom - RFI 10703 & RFI 08105 | 165829.5 | E: 165829.5; I: Not agreed; J: 165829.5; L: ID-C4242-MH-8862-21; P: SBJV to explain why the item is not certified at 100% - Is there works remaining?; R: 165829.5; S: 165829.5; T: Fitch taken as claimed by Ishtar.
24 | 35 | SOD 2 | VO No. 35 Rectification of Damages caused by Others on the installed Partitions in all areas | 154253.64 | E: 154253.64; I: Not agreed; J: 154253.64; L: ID/C4242/SO/6060/19; R: 154253.64; S: -; T: No Assessment
25 | 47 | SOD 2 | Block Wall Openings Required for LV Tray (Wild Air) for RT1, RT2 & RT3 in Basement Area | 136888.6 | E: 136888.6; I: Not agreed; J: 136888.6; L: ID-C4242-JA-6401-19; R: 136888.6; S: 118522.15; T: Fitch assessed rates of manpower and materials based on letter/invoices. Assessment for Materials is with OH&P
26 | 98 | SOD 4 | VO#98 Walls Tags Missing Information for C6 Package | 102815 | E: 102815; I: Not agreed; J: 102815; L: ID/C4242/MH/8464/20; R: 102815; S: 93468.49; T: Fitch taken as claimed by Ishtar without OH&P and Processing Cost
27 | 60 | SOD 2 | VO NO.60 Rectification of Damages caused on the installed partitions by MEP(Future metro ) - Residential towers | 100169 | E: 100169; I: Not agreed; J: 100169; L: ID/C4242/SM/6981/19; R: 100169; S: 69588.44; T: Fitch assessed rates and qty. Provided take off-sheet shows only Fitch's assessment. Assessment is with OH&P for Materials
28 |  |  |  | 3737299.56 | E: 3737299.56; G: -; H: -; J: 3737299.56; R: 3737299.56; S: 2817827.76
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51

## Table 4
[5 empty] | E | G | H | I | J | L | M | N | O | Q | R | S | T
[6 empty] | Actually in dispute |  |  |  | Paper trail of the variation |  |  |  | Mr Fitch's valuations |  | Mr Clarke comments on Mr Fitch's assessments
9 | VO No. | SD No. | Variation description | Final Claimed Amount | Amount claimed in SOD (AED) | Not certified but agreed by Ishtar | Not confirmed as agreed by Ishtar but certified in IPC 65 | Appears Agreed / Not agreed | Disputed value | Initial Submission, Letter Ref. | Date received by SBJV | SBJV Response | Current status of the VO (i.e who stopped responding) | Mr Fitch's understanding of the claimed amount (AED) | Fitch Assessment Values (AED) | Qty comments | Rate comments
10 | 57 | SOD 4 | VO No. 57 Architectural IFC Peruv ian Restaurant in Hotel Tower | 96639.36 | E: 96639.36; I: Not agreed; J: 96639.36; L: ID-C4242-MZ-6599-19; Q: 61333.67; R: 59361.4; S: Fitch taken as claimed by Ishtar w/o profit
11 | 118 | SOD 4 | VO#118 - CIP No. 2180 / EIP 0990 New WET Workshop- Basement Plan Area 11 rev (Mediterranean Restaurant) | 95425.79 | E: 95425.79; I: Not agreed; J: 95425.79; L: ID/C4242/MZ/8879/21
12 | 105 | SOD 4 | VO#105 Protection for MEP Services Proposed for BOH Areas-EIP 0837 | 89310 | E: 89310; I: Not agreed; J: 89310; L: ID-C4242-MH-8553-20
13 | 89 | SOD 4 | VO No. 89 Additional works related to RFI for C6 Package – Part 1 | 87361.72 | E: 87361.72; I: Not agreed; J: 87361.72; L: ID/C4242/MH/8341/20; Q: 179397.24; R: 172788.4; S: Fitch taken as claimed by Ishtar w/o profit
14 | 8 | SOD 2 | VO No. 08 Hotel Tower - Change of Door Nib Size in Hotel Tower | 86944 | E: 86944; I: Not agreed; J: 86944; L: ID/C4242/ST/5467/18
15 | 16 | SOD 4 | VO No. 16 Residential units - Discrepancy between A23 Series and Approved FLS Drawings (Shaft Walls) in Residence Tower | 68006.64 | E: 86341.83; I: Not agreed; J: 68006.64; L: ID/C4242/MZ/5520/18; Q: 68006.64; R: 78492.57; S: Fitch taken as claimed by Ishtar.
| 76 | SOD 4 | VO NO.76-Request for additional works by AHK | 61333.67 | 61333.67 |  |  | Not agreed | 61333.67 | ID-C4242-SM-7626-20 |  |  |  | 1011176.88 | 537912.07 | Mr. Fitch's assessment in "CER-1 App VO-86', tab 'Damages rectification evalutio' for qty., excludes manhours for overtime. | Mr. Fitch's assessment for manhour rate in "CER-1 App VO-86', tab 'Damages rectification evalutio', used a flat rate of 17aed/hour for all trades, from foreman to helper instead of the BOQ Day work rates.
16 |  |  |  |  | S: Mr. Fitch has applied the claimed quantities for materials in his assessment.; T: On rates for materials, Mr.Fitch have applied what is the claimed rates, except for rates that is without provided substantiation.
| 84 | SOD 4 | VO# 84 Additional nogging Ground & LG | 50504 | 50504 |  |  | Not agreed | 50504 | ID/C4242/JA/8183/20 |  |  |  | 4774499 | 2507367.28 | Fitch has done no review of the quantities claimed. He applied the claimed quantities in his assessment. | Mr. Fitch does not assess the addition rate claimed. Rather, he provides his own rate build up at 'CER-1 App VO-087 Assesment, tab titled 'FitchAssessment Rate Break down' Mr Fitch's rate build up is derived from 1 Lm of bulkhead (fire rated and non fire rated) based on Cantilever Suite Typical Bulkhead Details Drawing "Drawing ref TRA-ISH-SDG-PO-GEN-47900 Rev 03". (a) Material - Mr. Fitch has considered material rate from the PO enclosed in the SBJV Contra Charge letter ref RAP/SBJ/FLH/2.12.26/20/15366 and 10% of Material Cost for OH&P. (b) Labour - Mr Fitch calculated a 1 LM labour rate based on unsigned daywork sheets for the installation of 52 LM bulkhead. (c) Plant & Equipment/Tools - Mr. Fitch has provided a lump sum cost that is 10% of Material Cost.
Omission is considered to be based on the BOQ Rates.
17
18 | 31 | SOD 2 | Additional Wall Nogging for Wall Panelling Installation at Hotel Corridor (L5-8) in Hotel Tower | 47469.6 | E: 47469.6; I: Not agreed; J: 47469.6; L: ID-C4242-ST-5747-18
19 | 95 | SOD 4 | VO#95 Gas Pipes Shaft walls at Podium & Hotel Towers CIP 2303 | 43782.63 | E: 43782.63; I: Not agreed; J: 43782.63; L: ID/C4242/MH/8420/20; Q: 87361.72; R: 87361.72; S: Fitch taken as claimed by Ishtar.
20 | 107 | SOD 4 | 107.VO#107 Additional Walls at Third Floor Zone 04 - Related to DEC L 02076 | 42233 | E: 42233; I: Not agreed; J: 42233; L: ID-C4242-MH-8599-20; Q: 34459.95; R: 34459.95; S: Fitch taken as claimed by Ishtar.
21 | 90 | SOD 4 | VO No. 90 CIP 2258 Door Nib | 34459.95 | E: 34459.95; I: Not agreed; J: 34459.95; L: ID/C4242/SM/8325/20; Q: 281823.59; R: -; S: Assessed as Nil, awaiting Ishtar to provide documents that works has been executed on site.
22 | 103 | SOD 4 | VO#103 Additional Masonry Wall at Basement Zone 16 (DEC Letter 02465) | 34183 | E: 34183; I: Not agreed; J: 34183; L: ID-C4242-MH-8503-20
23 | 70 | SOD 4 | VO NO.70 Additional Works requested by III | 32440 | 32440 |  |  | Not agreed | 32440 | ID-C4242-SM-7279-20 |  |  |  | 2026936.38 | 1785804.8 | Mr Fitch has done no review of the quantities claimed. He has applied the claimed quantities in his assessment. | Mr Fitch does not assess the rates claimed. Rather, he provides his own rate build up at 'CER-1 App VO-93, tab titled 'Analysis'. The rate is built up with two different lengths and a height of 8m to derive a m2. An amount of AED 80 is applied to the m2 with a further 30% uplift applied. Mr Fitch's rate does not include OH&P.
| 67 | SOD 2 | Rectification of fire sealant damage caused by MEP subcontractor | 30588 | E: 30588; I: Not agreed; J: 30588; L: ID/4242/SM/7197/20; Q: 7699; R: 111761; S: Fitch assessed rates and qty. Measurement/Take off sheet provided is as per Fitch Assessment only.
24 |  |  |  |  | S: NO OH&P included.
25 | 116 | SOD 4 | VO#116 - CIP 1124 /EIP 0602 Architectural IFC Drawings - Bridge Suite | 29502 | E: 29502; I: Not agreed; J: 29502; L: ID/C4242/MZ/8813/21; Q: 43782.63; R: 43782.63; S: Fitch taken as claimed by Ishtar.
26 | 108 | SOD 4 | VO#108 Wall Nogging at Podium Level 2 | 24960 | E: 24960; I: Not agreed; J: 24960; L: ID-C4242-MH-8619-20; Q: 13631; R: 11853.33; S: Fitch taken as claimed by Ishtar without OH&P and Processing Cost
27 | 114 | SOD 4 | VO#114 Additional Walls in Basement Zone 06 - DEC 00646 | 22075 | E: 22075; I: Not agreed; J: 22075; L: ID-C4242-MH-8679-21; Q: 20879.63; R: 18156.2; S: Fitch taken as claimed by Ishtar without OH&P and Processing Cost
28 | 113 | SOD 4 | VO#113 EIPL 0835-EIP 0782- Mediterranean Restaurant FHC | 21417 | E: 21417; I: Not agreed; J: 21417; L: ID/C4242/MZ/8722/20; Q: 102815; R: 93468.49; S: Fitch taken as claimed by Ishtar without OH&P and Processing Cost
29 | 97 | SOD 4 | VO#97 Block Walls Demolition Related to RFI 06365 for C6 Package | 20879.63 | E: 7380; I: Not agreed; J: 20879.63; L: ID/C4242/MH/8463/20; Q: 6202; R: 5393.02; S: Fitch taken as claimed by Ishtar without OH&P and Processing Cost
30 | 109 | SOD 4 | VO No.109: Additional Walls at Mediterranean restaurant - Second Floor- related to DEC letter 02567 | 19093 | E: 19093; I: Not agreed; J: 19093; L: ID/C4242/MH/8637/20; Q: 13004; R: 11307.66; S: Fitch taken as claimed by Ishtar without OH&P and Processing Cost
31 | 14 | SOD 4 | VO No. 14 Additional Wall Noggin for TV. Bracket installation in Type A & B Guestrooms in Hotel Tower | 18130.2 | E: 15458.4; I: Not agreed; J: 18130.2; L: ID/C4242/ST/5284/18; Q: 3600; R: 3130.11; S: Fitch taken as claimed by Ishtar without OH&P and Processing Cost
32 | 106 | SOD 4 | 106.VO#106 Additional Walls at 22nd floor - Zone 03 - Related to DEC L 02551 | 17859 | E: 17859; I: Not agreed; J: 17859; L: ID-C4242-MH-8554-20; Q: 8210; R: 7139.22; S: Fitch taken as claimed by Ishtar without OH&P and Processing Cost
33 | 123 | SOD 4 | VO#123 Super Penthouse Service Elevator Shaft Enclosure | 15250.25 | E: 15250.25; I: Not agreed; J: 15250.25; L: ID/C4242/MZ/8907/21; Q: 3703; R: 11722.32; S: Fitch removed additional cost for demolition works and adapted cost for additional wall without OH&P
34 | 96 | SOD 4 | VO#96 Wall Demolishing Works Related to RFI 07658 for C6 Package | 13631 | E: 13631; I: Not agreed; J: 13631; L: ID/C4242/MH/8462/20; Q: 42233; R: 36724.65; S: Fitch taken as claimed by Ishtar without OH&P and Processing Cost
35 | 100 | SOD 4 | VO#100 Additional Walls for Dewa HV Cables Related to RFI 05843 | 13004 | E: 13004; I: Not agreed; J: 13004; L: ID/C4242/MH/8466/20; Q: 24960; R: 23874.92; S: Fitch taken as claimed by Ishtar without Processing Cost
36 | 45 | SOD 2 | Opening in Gypsum Board Walls in Utility Rooms of Residential Tower - RT2 (L01 to L03), RT3 (L01-L06) for Relocation of Electrical Points in Residence Tower | 12591.5 | E: 12591.5; I: Not agreed; J: 12591.5; L: ID/C4242/JA/6353/19; Q: 19093; R: 16602.25; S: Fitch taken as claimed by Ishtar without OH&P and Processing Cost
37 | 122 | SOD 4 | VO#122 - Mediterranean LG / GF - Missing Wall Tags / Discrepancy with ID | 10663.97 | E: 10663.97; I: Not agreed; J: 10663.97; L: ID/C4242/MZ/8898/21; O: N/A
38 | 120 | SOD 4 | VO#120 Additional Walls at Mediterranean Restaurant Ground Floor - RFI 09315 | 9493 | 9493 |  |  | Not agreed | 9493 | ID-C4242-MH-8881-21 |  |  |  | 1753661.48 | 1151504.64 | Mr Fitch has done no review of the quantities claimed. He has applied the claimed quantities in his assessment. | Mr Fitch does not assess the rates claimed. Rather, he provides his own rate build-up at 'CER-1 App VO-111, tab titled 'Analysis'. The rate is built up with a length and a height of 8m to derive a m2. An amount of AED 80 is applied to the m2 with a further 30% uplift applied. Mr Fitch's rate does not include OH&P, However total assessment has 10% OH&P.
5 | Appendix RER-1-QKC-2.1 - Mr Clarke's assessment summary (Variations)
6
7
8 |  |  |  |  | G: Actually in dispute; L: Paper trail of the variation; Q: Mr Fitch's valuations; S: Mr Clarke comments on Mr Fitch's assessments
9 | VO No. | SD No. | Variation description | Final Claimed Amount | Amount claimed in SOD (AED) | Not certified but agreed by Ishtar | Not confirmed as agreed by Ishtar but certified in IPC 65 | Appears Agreed / Not agreed | Disputed value | Initial Submission, Letter Ref. | Date received by SBJV | SBJV Response | Current status of the VO (i.e who stopped responding) | Mr Fitch's understanding of the claimed amount (AED) | Fitch Assessment Values (AED) | Qty comments | Rate comments
39 | 102 | SOD 4 | VO#102 Wall Type Changed Lower Ground Floor Zone 17 Related to RFI 07327 | 8210 | 8210 |  |  | Not agreed | 8210 | ID/C4242/MH/8477/20 |  |  |  | 1260247.97 | 1260247.97 | Mr Fitch has done no review of the quantities claimed. He has applied the claimed quantities in his assessment. | Mr Fitch has done no review of the rates claimed. He has applied the claimed rates in his assessment.
40 | 94 | SOD 4 | VO No. 94 Additional works related to RFI for C6 Package – Part 2 | 7699 | E: 7699; I: Not agreed; J: 7699; L: ID/C4242/MH/8400/20; Q: 21417; R: 21417; S: Fitch taken as claimed by Ishtar.
41 | 99 | SOD 4 | VO#99 Residential unit (3 BED TYPE 8) - kitchen Wall type Changed Related to RFI 05018 | 6202 | E: 6202; I: Not agreed; J: 6202; L: ID/C4242/MH/8465/20; Q: 22075; R: 22075.36; S: Fitch taken as claimed by Ishtar.
42 | 115 | SOD 4 | VO#115 Additional Walls at Basement Zone 02 - DEC 00840 | 5421 | E: 5421; I: Not agreed; J: 5421; L: ID-C4242-MH-8680-21; Q: 29502; R: 29502; S: Fitch taken as claimed by Ishtar.
43 | 124 | SOD 4 | VO#124 Additional Cement Board @ Ground Floor RFC 00625(RFI 13538) | 5264.58 | 38521.52 |  |  | Not agreed | 5264.58 | ID/C4242/MZ/8954/21 |  | Ishtar accepted the valuation of this VO in the amount of AED 5,264.58 (Excl. 5% for SBJV) in letter ID/C4242/MZ/9184/2021. |  | 774261 | 169509.83 | Mr.Fitch assessment for quantities only include quantities for wall partition 1.6 and 1.6u. He applied the claimed quantities in his assessment. | Mr.Fitch assessment for rates only include rates for wall partition 1.6 and 1.6u. He applied the claimed rates in his assessment. Rates is inclusiv e of 10% OH&P
44 | 119 | SOD 4 | VO#119 Additional Walls at Residential Tower - DEC 00655 | 4713.14 | E: 4713.14; I: Not agreed; J: 4713.14; L: ID-C4242-MH-8830-21; Q: 95425.79; R: 95425.79; S: Fitch taken as claimed by Ishtar.
45 | 104 | SOD 4 | VO#104 Alight Access Platform - Duct Rerouting SDIR 0330 | 3703 | E: 39730; I: Not agreed; J: 3703; L: ID-C4242-MH-8552-20; Q: 4713.14; R: 4713.14; S: Fitch taken as claimed by Ishtar.
46 | 101 | SOD 4 | VO#101 Wall Type Changed for Hotel suit Level 41 and 42 Related to RFI 06856 | 3600 | E: 3600; I: Not agreed; J: 3600; L: ID/C4242/MH/8467/20; Q: 9493; R: 9492.89; S: Fitch taken as claimed by Ishtar.
47
48 |  |  |  | 1194043.63 | E: 1265491.33; G: -; H: -; J: 1194043.63
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71

## Table 5
[5 empty] | E | F | G | H | I | J | K | L | M | N
[7 empty] | Actually in dispute |  |  |  |  | Mr Fitch's valuations
10 | VO No. | SD No. | Variation description | Final Claimed Amount | Amount claimed in SOD (AED) |  | Not certified but agreed by Ishtar | Not confirmed as agreed by Ishtar but certified in IPC 65 | Appears Agreed / Not agreed | Disputed value |  | Mr Fitch's understanding of the claimed amount (AED) | Fitch Assessment Values (AED) | Mr Clarke comments on Mr Fitch's assessments
11 | 137 | SOD 7 | THIS IS A CC VARIATION | 1047317.09 | 1047317.09 |  |  |  | Not agreed | 1047317.09 |  | 1047317.09 | 99310 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
12 | 138 | SOD 7 | THIS IS A CC VARIATION | 1993058.15 | 1993058.15 |  |  |  | Not agreed | 1993058.15 |  | 1993058.15 | 114385 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
13 | 139 | SOD 7 | THIS IS A CC VARIATION | 3358288.18 | 3358288.18 |  |  |  | Not agreed | 3358288.18 |  | 3358288.18 | 193048 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
14 | 140 | SOD 7 | THIS IS A CC VARIATION | 1384829.81 | 1384829.81 |  |  |  | Not agreed | 1384829.81 |  | 1384829.81 | 78315 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
15 | 141 | SOD 7 | THIS IS A CC VARIATION | 1170600.6 | 1170600.6 |  |  |  | Not agreed | 1170600.6 |  | 1170600.6 | 68187 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
16 | 142 | SOD 7 | THIS IS A CC VARIATION | 780624.05 | 780624.05 |  |  |  | Not agreed | 780624.05 |  | 780624.05 | 70256 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
17 | 143 | SOD 7 | THIS IS A CC VARIATION | 475319.65 | 475319.65 |  |  |  | Not agreed | 475319.65 |  | 475319.65 | 132265 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
18 | 144 | SOD 7 | THIS IS A CC VARIATION | 507325.24 | 507325.24 |  |  |  | Not agreed | 507325.24 |  | 507325.24 | 16775 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
19 | 145 | SOD 7 | THIS IS A CC VARIATION | 5651614.06 | 5651614.06 |  |  |  | Not agreed | 5651614.06 |  | 5651614.06 | 353701 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
20 | 146 | SOD 7 | THIS IS A CC VARIATION | 3772988.74 | 3772988.74 |  |  |  | Not agreed | 3772988.74 |  | 3772988.74 | 353701 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
21 | 147 | SOD 7 | THIS IS A CC VARIATION | 5255316.61 | 5255316.61 |  |  |  | Not agreed | 5255316.61 |  | 5255316.61 | 286723 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
22 | 148 | SOD 7 | THIS IS A CC VARIATION | 4917926.79 | 4917926.79 |  |  |  | Not agreed | 4917926.79 |  | 4917926.79 | 294068 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
23 | 149 | SOD 7 | THIS IS A CC VARIATION | 3888770.33 | 3888770.33 |  |  |  | Not agreed | 3888770.33 |  | 3888770.33 | 225693.95 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
5 | Appendix RER-1-QKC-2.1 - Mr Clarke's assessment summary (Variations)
6
7 | SOD 7 Variations
8
9 |  |  |  |  | G: Actually in dispute; L: Mr Fitch's valuations
10 | VO No. | SD No. | Variation description | Final Claimed Amount | Amount claimed in SOD (AED) |  | Not certified but agreed by Ishtar | Not confirmed as agreed by Ishtar but certified in IPC 65 | Appears Agreed / Not agreed | Disputed value |  | Mr Fitch's understanding of the claimed amount (AED) | Fitch Assessment Values (AED) | Mr Clarke comments on Mr Fitch's assessments
24 | 150 | SOD 7 | THIS IS A CC VARIATION | 3204051.23 | 3204051.23 |  |  |  | Not agreed | 3204051.23 |  | 3204051.23 | 189372.95 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
25 | 151 | SOD 7 | THIS IS A CC VARIATION | 6018368.26 | 6018368.26 |  |  |  | Not agreed | 6018368.26 |  | 6018368.26 | 363813.33 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
26 | 152 | SOD 7 | THIS IS A CC VARIATION | 4123373.22 | 4123373.22 |  |  |  | Not agreed | 4123373.22 |  | 4123373.22 | 249419.13 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
27 | 154 | SOD 7 | THIS IS A CC VARIATION | 3568889.27 | 3568889.27 |  |  |  | Not agreed | 3568889.27 |  | 3568889.27 | 208582.87 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
28 | 155 | SOD 7 | THIS IS A CC VARIATION | 4151142.38 | 4151142.38 |  |  |  | Not agreed | 4151142.38 |  | 4151142.38 | 240636.24 | Fitch Assessment is 10% of SBJV's Contra charged Amount. (Meaning 10% OHP allowance is stripped out by reducing the SBJV Contra Charged amount to 90% to produce a ‘net’ assessment, then 10% OHP percentage is then added to that net amount to reflect the ‘lost’ OHP. ).
29
30 |  |  |  | 55269803.66 | E: 55269803.66; G: -; H: -; J: 55269803.66
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53

## Table 6
[5 empty] | E | F | G | H | I | J | K | L | M | N | O | P
[7 empty] | Issued Variations (SVO) |  | Agreed by Ishtar |  | Cost Consultant Assessment |  | Certified in IPC 65
10 | VO No. | Variation description | Amount introduced in CER-1 (AED) | Initial Submission, Letter Ref. | CER-1 Assessment (AED) | Appears Agreed / Not agreed | Amount (AED) | SVO document ref. | Amount (AED) | Document demonstrating agreement | Amount (AED) | Doc ref. | Amount (AED) | Doc ref. | Disputed Amount (AED) | Mr Clarke comments
11 | 3 | Additional Manpower for MEP incorporation in M/s Ishtar Drawing. | 166408 | `ID-C4242-S T-5172-18 | E: 166408; F: N/A; O: 166408; P: This VO is superseded and included within VO No. 13.
12 | 4 | Additional Reinforcement for RF Metal Door Fixing in (Basement Floor) | 143162 | ID/C4242/ST/5185/18 | E: 143162; F: Agreed; I: 143162; J: ID/C4242/SM/8600/20
13 | 5 | Rectification of Damages caused on the installed partitions by other sub-contractors | 13609.86 | ID-C4242-S T-5285-18 | E: 12372; F: N/A; O: 13609.86; P: This item looks to be a duplicate of VO 15 below.
14 | 6 | CIP 101 (EIP 0278) Change partially Constructed DEW A Room from Hollow to Solid Block in Podium | 233210 | ID/C4242/ST/5880/18 | E: 233210; F: Agreed; M: 233209.52; P: The amount certified in IPC 65 is titled VO 138
15 | 7 | Release of Updated Architectural IFC Drawings – Basement Kitchen in Podium | 94870 | ID/C4242/ST/5106/18 | E: 94870; F: Agreed; G: 94870; H: (SVO-0041) TRA/SBJ/FLH/2.12.26/19/08306
16 | 9 | Release of Updated Architectural IFC Drawings - Empower Amendments in Podium | 87960 | ID/C4242/ST/5468/18 | E: 87960; F: Agreed; I: 87960.11; J: ID/C4242/ST/5874/18
17 | 10 | Masonry W all At Basement Zone 13&14 | 137239.55 | ID-C4242-S T-5469-18 | E: 124763.23; F: Not agreed; O: 137239.55; P: Unable to determine if SBJV (i) received as there is no received stamp, and (ii) responded, to letter ID/C4242/ST/5469/18.
18 | 11 | Cl 039 Aesthetic Improvements & Consolidation of MEP Services in Carpark in Podium | 92275.76 | ID-C4242-S T-5561-18 | E: 92275.76; F: Agreed; I: 92276; J: ID/C4242/ST/7719/2020
19 | 12 | Release of IFC Information to Proceed for Residences in Podium | 184430 | ID/C4242/MZ/5496/18 | E: 184430; F: Agreed; I: 184430.33; J: ID/C4242/ST/5874/18
20 | 15 | Rectification of Damages caused on the installed partitions by other sub-contractors | 13609.86 | ID-C4242-S T-5285-18 | E: 12372; F: N/A; O: 13609.86; P: This VO is superseeded by VO 35 (see ID/C4242/SO/6060/19 dated 31 Jan 2019)
21 | 17 | F3 Uncoordinated Design- Sliding Door Partition Thickness in Residence Tower | 1006560.61 | ID-C4242-S T-5560-18 | E: 1006560.61; F: Agreed; I: 1006560.61; J: ID/C4242/ST/7442/20
22 | 18 |  |  | ` | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
23 | 19 | Residential Units - (Level 14-17)- Additional W all Missing Information in Residence Tower | 3186.81 | ID/C4242/MZ/5548/18 | E: 3186.81; F: Agreed; I: 3261.46; J: ID/C4242/ST/5777/18
24 | 21 | Change of 1.8 wall type to 7.1 in HT1,2 and 3 in level 5,6 and 8 Room type ( A6.2, A6.2R, A5.2, A5.2R, A7.2, A7.2R ) in Hotel Tower | 36909 | ID/C4242/MZ/5607/18 | E: 36909; F: Agreed; I: 36909; J: ID/C4242/MZ/6418/19
25 | 22 | DEW A Mobile Generator Room IFC in Podium | 26222 | ID/C4242/MZ/5859/18 | E: 26222; F: Agreed; G: 26222; H: TRA/SBJ/FLH/2.12.26/20/16689 & ID/C4242/MZ/6003/19
26 | 23 | Residential Units ( Level 05-13 ) Additional W alls Missing Information in Residence Tower | 126361.73 | ID/C4242/MZ/5590/18 | E: 126361.73; F: Agreed; I: 126361.73; J: ID/C4242/ST/5777/18
27 | 24 | Residential units & Town Houses - Additioinal W alls Missing Information in Residence Tower | 34431 | ID/C4242/MZ/5619/18 | E: 34431; F: Agreed; I: 34430.8; J: ID/C4242/MZ/6419/19
28 | 26 | Additional W alls for FHC Residential Corridors & Core W all.:-Residential -Corridors-Additional wall for FHC- Missing information (L1-L28) AND Residential Units (Level 18-34) -Additional walls missing Information (FHC @ Core B in Residence Towe | 168333.91 | ID/C4242/MZ/5717/19 | E: 168333.91; F: Not agreed; I: 168333.91; J: ID/C4242/MZ/8540/2020
29 | 27 | RMU Architectural & Facade IFC Hotel & Residences in Podium | 268109.52 | ID/C4242/ST/5744/18 | E: 268109.52; F: Agreed; I: 268109.57; J: ID/C4242/MZ/6596/19
30 | 28 | Upstand Concrete kerb at louver doors and windows converted to solid block | 15677.37 | ID-C4242-S T-5745-18 | E: 14252; F: Not agreed; O: 15677.37; P: This Variation has been cancelled by Ishtar (see ID/C4242/ST/5773/18
31 | 29 | Additional W alls for FHC Hotel Corridors & Core W all in Hotel Tower | 366847.1 | ID/C4242/MZ/5719/19 | E: 366847.1; F: Agreed; I: 366847.1; J: ID/C4242/ST/7720/2020
32 | 30 | Additional Lining Request for W all Type at Basement in Podium | 14420.73 | ID/C4242/ST/5746/18 | E: 14420.73; F: Not agreed; I: 14420.73; J: ARC-COSTADV-000526
33 | 32 | (Upstand Concrete kerb at louver doors and windows converted to solid block | 14011.22 | ID-C4242-S T-5812-18 | E: 12737; F: Not agreed; O: 14011.22; P: Unable to determine if SBJV responded to letter ID/C4242/ST/5812/18. Ishtar rely on an RFI for this VO. The Consultant responded stating that the drawing already shows a row of conc. Block curb and that converting it to solid block is acceptable if that is the clarification required. This does not seem like a request to convert it. Furthermore, it appears that the items agreed in Variation No. 76 have incorporated the items included under this Vairation. see letter TRA/SBJ/FLH/2.12.28/19/11734
34 | 33 | Architectural & Interior Design IFC - Mediterranean Restaurant in Podium | 1083689 | ID-C4242-MZ-5873-18 | E: 1083689; F: Agreed; G: 1083689; H: TRA/SBJ/FLH/2.12.26/20/14614 & ID/C4242/MZ/6595/19
35 | 38 | Part 1 Block fair facing- Basement level (Zone 17,19 & 20) Provisional quantities value engineering confirmation for packages F9a & F9b in Podium | 68066.67 | ID/C4242/SM/6100/19 | E: 68066.67; F: Agreed; I: 68066.67; J: ID/C4242/SM/8071/2020
36 | 40 | Part 1 Re-measurement of Cement Board (Residential Units) in Combined Areas | 549872 | ID/C4242/MZ/ 6112/19 | E: 268313; F: Agreed; I: 549872.07; J: ID/C4242/MZ/7316/20
37 | 41 | Part 1 Updated Design BTU Locations (L01 - L17) Residential Towers | 976127.04 | ID-C4242-S M-6143-19 | E: 976127.04; F: Agreed; I: 976127.04; J: ID/C4242/SM/8022/2020
38 | 42 | EI-P No. 231 Release of IFC Information for Robatayaki Restaurant & Tunnel in Podium | 162833.2 | ID/C4242/MZ/5992/19 | E: 162833.2; F: Agreed; I: 162833.2; J: ID/C4242/MZ/8387/2020
39 | 43 | EI-P No. 475 Architectural IFC Drawings - Food Court (Rev. 01) in Podium | 189486.62 | ID-C4242-MZ-6199-19 | E: 189486.62; F: Agreed; I: 189486.62; J: ID/C4242/ST/6584/19
40 | 44 | Additional Steel Support for the Marble Partition (Part 1) in Podium | 2773187.34 | ID-C4242-MZ-6213-19 | E: 2773187.34; F: Agreed; I: 2773187.34; J: ID/C4242/MZ/8677/2020
41 | 46 | SDIR No 150 Shaft wall construction in Hotel Tower | 505878.36 | ID-C4242-S T-6529-19 | E: 505878.36; F: Agreed; I: 505878.36; J: SBJV issued the Cost Consultant's assessment on 7 March 2020 (RAP/SBJ/DMC/2.12.26/20/ 14874) in the amount of AED 531,172 (505,878.10 + 5% for SBJV). Ishtar accepted the amount of AED 531,172 in letter ID/C4242/ST/7451/20.
42 | 48 | Architectural & Interior Design IFC Drawings-Lower Ground Area -9 in Podium (Family Lounge) | 268517 | ID-C4242-MZ-6405-19 | E: 268517; F: Agreed; G: 268517.59; H: TRA/SBJ/FLH/2.12.26/19/16641
43 | 50 | Cement Board for Town House in Residence Tower | 57504.03 | ID-C4242-MZ-6532-19 | E: 57504.03; F: Agreed; I: 57504.03; J: ID/C4242/MZ/8654/2020
| A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P
5 | A: Appendix RER-1 QKC-2.1 - Mr Clarke's assessment summary (Variations)
6
7 | A: Summary of CER-1 additional variations
8
9 | G: Issued Variations (SVO); I: Agreed by Ishtar; K: Cost Consultant Assessment; M: Certified in IPC 65
44 | A: 51; B: Sliding door for Town House in Residence Tower; C: 132704.06; D: ID-C4242-MZ-6533-19; E: 132704.06; F: Agreed; I: 132704; J: ID/C4242/ST/7445/20
45 | A: 52; B: Peruvian & British Restaurant in Hotel Tower; C: 198960.33; D: ID-C4242-MZ-6534-19; E: 198960.33; F: Agreed; I: 198960.33; J: ID/C4242/MZ/7171/19
46 | A: 53; B: Release of Updated IFC Information for Architectural P211 SPA & ball room in Hotel Podium; C: 719849.11; D: ID-C4242-MZ-6571-19; E: 719849.11; F: Agreed; I: 719849.11; J: ID/C4242/MZ/7468/20
47 | A: 54; B: Architectural IFC for Spanish & Persian Restaurant in Hotel Podium; C: 56202.14; D: ID-C4242-MZ-6572-19; E: 56202.14; F: Agreed; I: 56202.14; J: ID/C4242/MZ/6682/19
48 | A: 55; B: Structural & Architectural IFCs - Penthouse 3; C: 85565; D: ID-C4242-MZ-6580-19; E: 85565; F: Agreed; I: 85565; J: ID/C4242/MZ/6830/19
49 | A: 56; B: Architectural IFC for Persian Restaurant in Hotel Podium; C: 28809; D: ID-C4242-MZ-6587-19; E: 28809; F: Agreed; I: 28808.79; J: ID/C4242/MZ/7274/20
50 | A: 59; B: Release of IFC Information to Proceed for Podium; C: 81390.12; D: ID-C4242-MZ-6640-19; E: 81390.12; F: Agreed; I: 81390.12; J: ID/C4242/MZ/7463/20
51 | A: 61; B: Updated Architectural IFC (Rev 01) for Basement; C: 14516; D: ID-C4242-MZ-6987-19; E: 14516; F: Agreed; I: 14516; J: ID/C4242/MZ/7183/20
52 | A: 63; B: Updated Architectural IFC for All Day Dining; C: 163319; D: ID-C4242-MZ-7062-19; E: 163319; F: Agreed; I: 163318.72; J: ID/C4242/MZ/7662/2020
53 | A: 66; B: Architectural IFC for Level 21 to 24 Sky Pool; C: 376709; D: ID-4242-MZ-7112-19; E: 376709; F: Agreed; I: 376709; J: ID/C4242/MZ/7598/2020
54 | A: 69; B: RAW requested by Al Abbar subcontractor; C: 22800; D: ID-4242-S M-7278-20; E: 22800; F: Agreed; I: 22800; J: ID/C4242/JA/8708/20
55 | A: 72; B: FHC at Residential Core; C: 182225.71; D: ID-C4242-JA-6621-20; E: 182225.71; F: Agreed; I: 182225.68; J: ID/C4242/JA/8618/20
56 | A: 77; B: Architectural IFC for Guard House & PRS Gas Station (Architectural IFC Submission); C: 37587; D: ID-C4242-MZ-7697-20; E: 37587; F: Agreed; I: 37586.67; J: ID/C4242/MZ/7940/2020
57 | A: 78; B: Architectural IFC for Residential Penthouses 1,2 and 2.1; C: 74042.71; D: ID-C4242-MZ-7729-20; E: 74042.71; F: Agreed; I: 74042.71; J: ID/C4242/MZ/8651/2020
58 | A: 80; B: EI-P 0607 CIP 1150 - SDIR 150 & FCN 03755- Tower HT1, HT2, HT3, Sub Risers Shaft W all Construction-Level 21 up to Level 40; C: 249531.88; D: ID/C4242/SM/7993/20; E: 249531.88; F: Agreed; I: 249531.88; J: ID/C4242/SM/8222/2020
59 | A: 88; B: Additional Steel Support for the Marble Partition (Part 02) in Podium; C: 1370321.26; D: ID/C4242/MZ/8300/20; E: 1370321.26; F: Agreed; I: 1370321.26; J: ID/C4242/MZ/8678/2020
60 | A: 92; B: Robatayaki Restaurant Architectural and BOH (F9) Updated Drawings (Additional W ork); C: 5817.25; D: ID/C4242/MZ/8391/20; E: 5817.25; F: Agreed; I: 5817.25; J: ID/C4242/MZ/8539/2020
61 | 110 |  |  | ` | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
62 | A: 125; B: Cake and Ice Cream Shops W orks - TIME-PM-ADV-000907; C: 37980.89; D: ID/C4242/MZ/8954/21; E: 37980.89; F: Agreed; I: 37980.89; J: ID/C4242/MZ/9127/2021
63 | A: 128; B: Mediterranean Restaurant- Missing Block/Partitions- TIME- PM-ADV-000956 & 000965; C: 49630; D: ID/C4242/MZ/8994/21; E: 49630; F: Agreed; I: 49630; J: ID/C4242/MZ/9305/2021
64 | A: 129; B: Release of Updated IFC Lower Ground Zone 19 - DEC Letter 03014; C: 3397; D: ID-C4242-MH-9070-21; E: 3397; F: Agreed; I: 3397; J: ID/C4242/MZ/9359/2021
65 | A: 130; B: Spa Lap Pool & Spanish W ater Feature Plantroom Updated Drawings – IFC Submission (Basement Zone 16, DEC Letter 03303); C: 10652; D: ID-C4242-MH-9125-21; E: 10652; F: Agreed; I: 10652; J: ID/C4242/MZ/9185/2021
66 | A: 131; B: Additional Dry W all Partition at HT1 Level 44; C: 76346; D: ID/C4242/MZ/9157/21; E: 76346; F: Not agreed; O: 76346; P: Unable to determine if SBJV responded to Ishtar's letter ID/C4242/MZ/9157/21.
67 | A: 132; B: Modification of Relocating the CRAC Units for the Hotel at Beasement Zone 07 & 17; C: 9181; D: ID/C4242/MZ/9182/21; E: 9181; F: Agreed; I: 9181; J: ID/C4242/MZ/9259/2021
68 | A: 133; B: C6-Additional Cement Board at Hotel Level 22 Locker Room; C: 5495.7; D: ID/C4242/MZ/9203/21; E: 5496; F: Not agreed; O: 5495.7; P: Unable to determine if SBJV responded to Ishtar's letter ID/C4242/MZ/9203/21.
69 | A: 134; B: L29 Sky Court Revised IFC Submission; C: 29606; D: ID/C4242/MZ/9244/21; E: 29606; F: Agreed; I: 29606; J: ID/C4242/MZ/9295/2021
70 | A: 135; B: L29 Skycourt W ash Room Finishes RFI#14333; C: 6583.4; D: ID/C4242/MZ/9245/21; E: 6583; F: Not agreed; O: 6583.4; P: Unable to determine if SBJV responded to Ishtar's letter ID/C4242/MZ/9245/21.
71 | A: 136; B: Additional partition required for W eather tightness of Building Envelope @ RT3 L39-40; C: 57753; D: ID/C4242/MZ/9274/21; E: 57753; F: Agreed; I: 55848; J: ID/C4242/MZ/9516/2021
72 | 153 | C6 -Fish Tank Service Room- IFC Submission | 114715.08 | ID/C4242/MZ/9334/21 | 72890 | Not agreed |  |  |  |  | 57730 | RAP/SBJ/FLH/2.12.26/21/24001 |  |  | 56985.08 | Unsure whether the balance of AED 56,985.08 is still disputed by Ishtar.
73 | A: PS; B: Value Engineering; C: 900000; E: 900000; F: Agreed; M: 900000; P: Amount certified in IPC 65 is titled VO 10
74
75 | C: 14984696.93; E: 14643661.12; G: 1473298.59; I: 11812662.24; K: 57730; M: 1133209.52; O: 505966.04

## Table 7
[5 empty] | E | F | G | H |  | I | J | K | L
[6 empty] | Actually in dispute |  |  |  |  | Paper trail of the variation
10 | VO No. | SD No. | Variation description | Final Claimed Amount |  | Not certified but agreed by Ishtar | Appears Agreed / Not agreed | Disputed value |  |  | Initial Submission, Letter Ref. | Date received by SBJV | SBJV Response
11 | 156 | - | DEC 03578 Changes in Basement (Area 16 & 19) Updated Architectural Drawings and MEP Sketches | 27835 |  | 27293 | Agreed | - |  |  | ID/C4242/MZ/9501/21 | 2021-09-06 | Ishtar accepted the valuation of this VO in the amount of AED 27,293.00 (Excl. 5% for SBJV) in letter ID/C4242/MZ/9538/2021.
12 | 157 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 3257888.78 |  |  | Not agreed | 3257888.78
13 | 158 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 4175985.74 |  |  | Not agreed | 4175985.74
14 | 159 | - | Penthouse 3501 - CHW provision to L36 Pool Plant room | 7251 |  | 7252 | Agreed | - |  |  | ID/C4242/MZ/9697/21 | 2021-11-30 | Ishtar accepted the valuation of this VO in the amount of AED 7,252.00 (Excl. 5% for SBJV) in letter ID/C4242/MZ/9749/2022.
15 | 160 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 5335740.34 |  |  | Not agreed | 5335740.34
16 | 161 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 5671204.37 |  |  | Not agreed | 5671204.37
17 | 162 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 2393234.07 |  |  | Not agreed | 2393234.07
18 | 163 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 1184750.21 |  |  | Not agreed | 1184750.21
19 | 164 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 624208.92 |  |  | Not agreed | 624208.92
20 | 165 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 438730.74 |  |  | Not agreed | 438730.74
21 | 166 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 579781.12 |  |  | Not agreed | 579781.12
22 | 167 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 624396.67 |  |  | Not agreed | 624396.67
23 | 168 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 756285.19 |  |  | Not agreed | 756285.19
24 | 169 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 1180879.8 |  |  | Not agreed | 1180879.8
25 | 170 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 576442.15 |  |  | Not agreed | 576442.15
26 | 171 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 466773.08 |  |  | Not agreed | 466773.08
27 | 172 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 86353.81 |  |  | Not agreed | 86353.81
28 | 173 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 72539.51 |  |  | Not agreed | 72539.51
29 | 174 | - | THIS IS A CC VARIATION (Not claimed in SOC) | 98481.68 |  |  | Not agreed | 98481.68
30
31 |  |  |  | 27558762.18 |  | 34545 |  | 27523676.18
Fq footer Page 1 of 1 | [8 empty] | SBJV v ISHTAR cd35f42180becb827921a6bad07dab247e10bb4fc1922f4d17b9a2b8b942d1c6 Further additional VOs